## Analysis & Conclusions
DTG RAHP – Risk & Harm Register v3 ¦ Harms Prevention Analysis & Conclusions for Standards Development ¦ Updated March 2026 with DTG Credential Spec v0.3 review
Working Draft · DTG Credentials Task Force · Derived from: VTC Bootstrapping Draft v3, Personas Analysis, DTGWG GitHub Discussions, RAHP User Stories Framework
1. Headline Risk Statistics
Total risks identified | 35 across 10 RAHP risk categories (31 original + 4 new from DTG Credential Spec v0.3 review)
High severity risks | 20 of 31 (64%)
Medium severity risks | 11 of 31
High severity AND high likelihood (priority action) | 4 risks — these are the immediate standards-development priorities
Controls defined | 56 controls (CT-01–CT-56) — 8 new controls added from DTG Credential Spec v0.3 analysis
Guardrails defined | 18 guardrails (GR-01–GR-18) — GR-18 (R-DID Migration Phase Gate) added from spec review
Assurance tests defined | 18 assurance tests (AT-01–AT-18) — AT-18 (R-DID migration verification) added from spec review
Risk categories with 100% High severity | AI Agents (4/4 High), Systemic (3/3 High)
2. The Five Most Critical Harm Types
C1. Trust Graph Integrity / Identity Fraud (combined)
Affects 9 High-severity risks across Identity, AI Agents, and Systemic categories. This is the existential harm: if the trust graph cannot be trusted, the entire DTG architecture fails. Sybil proliferation, AI-mediated synthetic identity generation, anchor collusion, and registry manipulation all attack the same fundamental property. Standards MUST define uniqueness enforcement and vouching anomaly detection as normative requirements.
C2. Human Rights Violations — Revocation, Exclusion, Surveillance
Affects 6 High-severity risks (RK-CR01, RK-HX02, RK-HX03, RK-EX01, RK-ID02, RK-SY02). The DTG architecture creates novel human rights risks: unjust revocation without due process, discriminatory vouching baked into web-of-trust structures, reputational harm from public revocation status, and state surveillance enabled by membership data linkability. These are not edge cases — they are structural features of the architecture that require normative mitigation.
C3. Governance Failure / Capture
Affects 7 High-severity risks across Governance, Identity, and Systemic. Genesis policy capture, governance transition failure, anchor collusion, and CIB in governance all represent scenarios where legitimate governance structures are compromised or absent. The bootstrapping phase is the most dangerous: power is maximally concentrated and oversight mechanisms do not yet exist.
C4. Privacy / Data Protection
Affects 5 risks (Medium–High). Over-disclosure in credential schemas, M-DID linkability, ZKP implementation failures, and the chilling effect on participation all represent privacy harms that are specifically enabled by the decentralised architecture — not prevented by it. GDPR, eIDAS 2.0, and emerging national digital identity laws create legal exposure if these are not addressed normatively.
C5. AI-Specific Attack Surface
All 4 AI Agent risks are rated High severity. The DTG architecture has no current normative provisions for non-human participants, yet AI agents are explicitly in scope (DTGWG charter). Agent scope creep, stale-agent-after-revocation, AI-mediated Sybil generation at scale, and LLM-powered social engineering represent a novel threat class that existing identity standards do not address.
3. Top Guardrails by High-Risk Coverage (Most Important Phase Gates for Standards)
Rank | Guardrail ID | Guardrail Name | High Risks Addressed | Total Risks | Why It Matters for Standards | Category | Linked ATs
1 | GR-06 | Privacy-Preserving Proofing Option | 8 | 8 | Highest risk coverage of any single guardrail (8 risks, 5 High). This is the primary technical lever for privacy, non-discrimination, and data minimisation. Without it, GDPR compliance, social exclusion, and surveillance risks are unmitigated. | Human Experience / Technology | AT-06
2 | GR-09 | Privacy-Preserving Revocation Disclosure | 6 | 8 | Second-highest coverage (8 risks). Controls revocation-related privacy, cross-VTC contamination, and member identity protection. Also structurally linked to anti-surveillance and human rights protections. | Technology / Governance | AT-09
3 | GR-07 | Uniqueness Enforcement Mechanism | 4 | 5 | Blocks the Sybil / AI-mediated identity fraud cluster (5 risks, 4 High). The most critical open issue in the bootstrapping draft. Must be resolved before Phase 4 or formally risk-accepted. | Technology / Governance | AT-07
4 | GR-10 | Multi-Party Registry Write Authorisation | 3 | 4 | Protects against registry manipulation, state coercion, and trust graph capture (4 risks, 3 High). Without multi-party authorisation, a single compromised actor can corrupt the entire community's trust graph. | Technology / Governance | AT-10
5 | GR-14 | Non-Human Actor Detection | 3 | 3 | Addresses the entire AI-mediated attack cluster (3 risks, all High). Currently no normative standard addresses this. The guardrail must be defined before Phase 4 opens. | Technology / Governance | AT-14
6 | GR-03 | Trust Anchor Diversity Policy | 3 | 3 | Addresses anchor collusion, discriminatory vouching, and systemic graph capture (3 risks, all High). Diversity is a human rights and security requirement simultaneously. | Governance / Human Experience | AT-03
7 | GR-08 | Revocation Due Process | 2 | 4 | Addresses 4 risks across the revocation lifecycle (2 High, 2 Medium). Without due process guarantees, revocation becomes a tool for arbitrary exclusion or political targeting. | Governance / Human Experience | AT-08
8 | GR-12 | Agent Delegation Scope Constraint | 2 | 2 | Addresses both AI agent High risks. No current DTG specification covers agent delegation. This guardrail is required to make the benign agent use case safe. | Technology / Governance | AT-12
4. Top Controls by High-Risk Coverage (Priority Implementation Candidates for Standards)
Rank | Control ID | Control Name | Type | High Risks | Rationale for Standards Priority | × | ×
1 | CT-08 | Uniqueness Enforcement Mechanism | Technical | 3 | The single most important technical control. Addresses Sybil proliferation, AI-mediated Sybil generation, and the open issues cluster. Must be a normative SHOULD/MUST in the DTG credential spec before Phase 4.
2 | CT-34 | Behavioural Anomaly Detection for Non-Human Actors | Technical | 3 | Required before Phase 4 opens (per GR-14). Addresses AI-mediated Sybil generation and trust graph capture. Currently no normative standard exists for non-human actor detection in VC-based trust systems.
3 | CT-45 | Multi-Party Registry Write Authorisation | Technical | 3 | Protects the entire trust registry from single-point-of-failure attacks. A normative MUST in any DTG credential specification. Directly underpins GR-10.
4 | CT-04 | Trust Anchor Diversity Policy | Governance | 3 | Required before Phase 2 opens. Simultaneously addresses anchor collusion, discriminatory vouching, and trust graph capture. Should be a normative SHOULD with a minimum diversity metric specification.
5 | CT-09 | Vouching Pattern Anomaly Detection | Technical | 2 | Complements uniqueness enforcement. Detects coordinated Sybil vouching rings before they pass admission thresholds. A normative SHOULD for Phase 4.
6 | CT-15 | Pseudonymous Per-VTC M-DID Design | Technical | 2 | Foundational privacy protection. Prevents cross-community profiling and reduces state surveillance risk. Should be a normative MUST in the DTG credential schema specification.
7 | CT-24 | Privacy-Preserving Revocation Disclosure | Technical | 2 | Protects members from public identity exposure during revocation. Addresses both High-severity human rights risks in the revocation lifecycle. A normative MUST.
8 | CT-30 | Cryptographic Delegation Scope Constraints | Technical | 2 | Required for safe AI agent participation in VTCs. No current standard addresses agent delegation in VC-based trust systems. A normative MUST for any agent-capable VTC implementation.
9 | CT-32 | Agent Liveness Check on Operator VMC | Technical | 2 | Prevents stale agent access after operator revocation. A normative MUST for agent credential lifecycle management.
10 | CT-10 | Non-Discriminatory Admission Criteria | Governance | 2 | Equality law and human rights requirement simultaneously. Must be a normative MUST in the VTC governance framework specification.
5. Conclusions — Priority Requirements for DTG Credential Standards
REC-1 NORMATIVE: Uniqueness Enforcement as Phase-Gate
GR-07 and CT-08 must become normative MUST requirements in the DTG credential specification. The VTC must define and document its uniqueness enforcement mechanism before Phase 4 opens. This is the single highest-coverage control requirement identified in this analysis, addressing Sybil proliferation, AI-mediated identity fraud, and the open issues cluster simultaneously. The specification should define at least three acceptable uniqueness mechanisms (ZKP personhood proof, trusted IDVP quorum, social recovery) and require governing bodies to select and document one.
REC-2 NORMATIVE: AI Agent Governance as First-Class Specification Area
All four AI Agent risks are rated High severity. The DTG credential specification must include a dedicated AI agent governance chapter covering: (a) cryptographic delegation scope constraints (CT-30) as a normative MUST; (b) operator VMC liveness checks before agent actions (CT-32) as a normative MUST; (c) non-human actor detection as a Phase 4 pre-condition (GR-14). This is a gap in all existing VC/DID standards — none address autonomous agent participation in trust graphs.
REC-3 NORMATIVE: Privacy-Preserving Revocation as Core Specification Requirement
GR-09 (Privacy-Preserving Revocation Disclosure) and CT-24 address 8 risks in total. The specification must require privacy-preserving revocation status mechanisms (e.g. W3C Status List 2021 with ZKP) as a normative MUST, not an optional feature. VTC-scoped revocation (CT-26) must also be normative: cross-VTC revocation contamination is a human rights risk that arises directly from the decentralised architecture.
REC-4 NORMATIVE: Non-Discriminatory Admission and Alternative Identity Proofing
RK-ID02 (Social Graph Privilege Exclusion) and RK-HX02 (Discriminatory Vouching) are both rated High severity and High likelihood — the most urgent combination in the dataset. The specification must require: (a) published non-discriminatory admission criteria; (b) at least one admission pathway not requiring conventional government-issued ID; (c) a documented appeals process for denied applicants. These are simultaneously legal requirements under equality and human rights law in most jurisdictions.
REC-5 NORMATIVE: Multi-Party Registry Write Authorisation
CT-45 and GR-10 address trust graph capture, state coercion, and registry manipulation. Multi-party write authorisation must be a normative MUST in the DTG trust registry specification. The specification should define minimum threshold requirements (e.g. 2-of-3 for small VTCs, higher thresholds at scale) and require tamper-evident audit trails for all writes.
REC-6 RECOMMENDED: Formal Threat Model as Standards Deliverable
GR-16 and CT-48 require a formal threat model. The DTGWG should publish this as a standalone deliverable alongside the credential specification. The threat model should be normatively referenced in the specification so that implementations can demonstrate conformance.
REC-7 RECOMMENDED: UX Design Principles as Normative Standards Annex
RK-NM01 is rated High severity and High likelihood — and the DTGWG itself acknowledges UX as 'the single hardest problem'. Sovereign wallet UX design principles (CT-20) and non-technical user onboarding testing requirements (CT-21) should be published as a normative annex to the credential specification, not left to individual implementations. Poor UX creates security failures, not just usability problems.
REC-8 PROCESS: Mandatory Open Issues Resolution Before Phase 4
GR-17 requires the four bootstrapping open issues to be formally resolved or risk-accepted before Phase 4. The DTGWG standards process should define a formal phase-gate procedure: any VTC implementation claiming conformance to the DTG specification must demonstrate that each open issue has either a documented mitigation or a signed risk acceptance with a review date.
6. Key Findings from DTG Credential Specification v0.3 Review (March 2026)
6a. What the spec gets right (reducing existing risks)
The R-DID MUST per-relationship (§5.2) reduces RK-ID05 likelihood from Medium to Low. Bilateral VRC signatures partially implement GR-04, raising per-edge sybil cost. The Witness Credential (VWC §7.3) provides a new technical counter to RK-AI04. Format-agnostic ZKP design supports algorithm agility for RK-CY02. PHC as governance-defined VMC (§9) correctly prevents self-asserted personhood claims.
6b. New risks introduced by spec design choices
RK-SC03 (VRC Over-Disclosure): No normative requirement to use annotation credentials for supplementary data — implementers may embed rich data in core VRCs, undermining ZKP privacy. RK-SC04 (M-DID Exception): M-DID bootstrapping permission with no migration trigger can permanently undermine the R-DID privacy model. RK-CR04 (VEC Manipulation): Open-ended endorsement structure enables reputation fraud. RK-G05 (Governanceless VTC): No normative governance pre-condition for credential compliance.
6c. Highest-priority gaps remaining after spec v0.3
1. Uniqueness enforcement (GR-07, CT-08) — completely absent from spec. 2. Revocation due process and privacy (GR-08, GR-09, CT-23–26) — deferred to trust registries with no normative hook. 3. AI agent governance (GR-12–14, CT-51–52) — agent M-DIDs permitted with no delegation or liveness requirements. 4. JSON-LD context and conformance test suite (CT-18–19) — not yet published as resolvable artefacts. 5. VIC role embedding open question (§6.1) — unresolved design question with governance implications.
6d. Spec commentary recommendation status
Critical (before Implementer's Draft): R1 (Non-Human §10), R2 (Uniqueness levels), R3 (Revocation placeholder), R4 (VIC roles). High (this draft cycle): R5 (JSON-LD context), R6 (VRC data min), R7 (R-DID trigger normative), R8 (governance conformance class). Recommended: R9 (VWC SHOULD for anchors), R10 (VEC co-membership), R11 (ZKP conformance roadmap).

## Risk & Harm Register
DTG RAHP – Risk & Harm Register v4 ¦ Affected Personas replaced by Affected Metrics (M-xx) — metrics link back to personas via Trust Metrics sheet
Guardrails (GR-xx) = non-negotiable phase gates ¦ Controls (CT-xx) = risk-reducing ¦ Assurance Tests (AT-xx) = evidence ¦ Metrics (M-xx) = measurable indicators linking risks to personas
Risk ID | Risk Name | Category | VTC Phase | Risk Description | Harm Type | Severity | Likelihood | Harm Description | Affected Metrics (M-xx → see Trust Metrics) | Linked US | Linked SC | Phase Gate Guardrails (GR-xx) | Additional Controls (CT-xx) | Assurance Tests (AT-xx) | Linked EPICs | Standards Priority
RK-G01 | Genesis Policy Capture | Governance | Phase 1 | The initiator hard-codes biased, self-serving, or exclusionary policies at genesis before any oversight mechanism exists. Phase 1 concentrates all power in one person; these policies may persist and shape the entire community lifecycle. | Governance Failure | High | Medium | Biased or discriminatory membership criteria embedded permanently; initiator retains unchecked authority; downstream decisions tainted by flawed genesis assumptions. | M-01: Anchor Diversity Index M-16: Governance Response Time to Security Findings | US-01 | SC-01 | GR-01, GR-02 | CT-01, CT-02 | AT-01, AT-02 | EPIC-1, EPIC-13 | ●●● Must address
RK-G02 | Governance Transition Failure | Governance | Phase 1–2 | The initiator's elevated authority is never formally transitioned to the governing body or anchors. The VTC continues to depend on a single person for governance decisions beyond the bootstrapping period. | Governance Failure | High | Low | Single point of governance failure; community paralysed or captured if initiator unavailable, coerced, or acting in bad faith. | M-01: Anchor Diversity Index M-16: Governance Response Time to Security Findings | US-01, US-02 | SC-01, SC-02 | GR-02 | CT-03 | AT-02 | EPIC-13 | ●●● Must address
RK-G03 | Anchor Homogeneity / Collusion Cluster | Governance | Phase 2 | Trust anchors are selected from a single social, geographic, or organisational network, creating a homogeneous cluster that can collude, share bias, or be collectively coerced. | Trust Graph Integrity | High | Medium | Coordinated anchor collusion enables mass fraudulent admissions; single-jurisdiction anchors vulnerable to state coercion; cultural bias embedded in vouching practices. | M-01: Anchor Diversity Index M-05: Anomaly Detection Hit Rate (Vouching) M-10: Jurisdictional Concentration | US-02, US-03 | SC-02, SC-09 | GR-03, GR-11 | CT-04, CT-05 | AT-03, AT-11 | EPIC-2, EPIC-13 | ●●● Must address
RK-G04 | Governance Bandwidth Exhaustion | Governance | Ongoing | Governing body capacity is overwhelmed — naturally through growth or deliberately through bad-faith abuse of governance mechanisms. | Governance Failure | Medium | Medium | Backlogs in admission, appeals, revocation; legitimate members denied timely due process; community trust in governance erodes. | M-07: Appeals Process Response Time M-11: Bad-Faith Appeals Rate | US-06, US-12 | SC-06, SC-12 | GR-08, GR-15 | CT-06, CT-07 | AT-08, AT-15 | EPIC-11, EPIC-13 | ●● Should address
RK-ID01 | Sybil Identity Proliferation | Identity | Phase 3–4 | A malicious actor creates multiple M-DIDs and uses coordinated vouching to pass multi-VRC admission thresholds. Uniqueness enforcement is an explicitly open issue in the VTC Bootstrapping Draft. | Trust Graph Integrity; Identity Fraud | High | High | Adversary gains disproportionate influence; voting and governance captured; legitimate members outvoted or silenced. | M-03: VRC Reciprocity Rate M-05: Anomaly Detection Hit Rate (Vouching) M-14: Sybil Cluster Detection Rate | US-07, US-10 | SC-07 | GR-04, GR-07 | CT-08, CT-09 | AT-04, AT-07 | EPIC-7, EPIC-8, EPIC-3 | ●●● Must address
RK-ID02 | Social Graph Privilege Exclusion | Identity | Phase 3–4 | The web-of-trust model structurally advantages applicants with pre-existing social connections. Those with non-dominant cultural backgrounds or limited digital literacy are disproportionately excluded. | Discrimination; Exclusion | High | High | Marginalised individuals unable to obtain required VRCs; VTC becomes homogeneous; human rights implications where VTC access enables civic or economic participation. | M-09: ZKP / Selective Disclosure Uptake M-12: Member Admission Denial Rate | US-04 | SC-03, SC-04 | GR-06 | CT-10, CT-11 | AT-06 | EPIC-10, EPIC-12 | ●●● Must address
RK-ID03 | IDVP Breach / Cascading Invalidation | Identity | Phase 4 | An IDVP suffers a data breach, is deregistered, or issues fraudulent IDVCs. Members admitted using those credentials face re-verification or revocation with no clear pathway. | Data Breach; Identity Fraud; Service Disruption | High | Medium | Mass credential invalidation; personal identity data exposed; fraud ring may have obtained IDVCs through compromised IDVP; re-verification creates accessibility barriers. | M-04: IDVC Issuer Verification Rate M-13: Credential Expiry-to-Renewal Latency | US-05 | SC-05 | GR-05, GR-09 | CT-12, CT-13 | AT-05, AT-09 | EPIC-4, EPIC-9 | ●●● Must address
RK-ID04 | DID Document Manipulation | Identity | All phases | An adversary manipulates DID documents to substitute or forge public keys, enabling impersonation of legitimate members or anchors. DID document storage is an open issue in the bootstrapping draft. | Identity Fraud; Trust Graph Integrity | High | Low | Fraudulent credential presentations accepted as genuine; impersonated anchors used to admit sybil members; member credentials stolen and replayed. | M-15: DID Document Integrity Verification Rate M-06: Registry Write Auth Failure Rate | US-07 | SC-08 | GR-10 | CT-14 | AT-10 | EPIC-7, EPIC-8 | ●●● Must address
RK-ID05 | M-DID Linkability Across VTCs | Identity | All phases | If a member uses the same M-DID across VTCs, or if the trust registry exposes sufficient metadata, an adversary can construct a cross-community profile. **SPEC UPDATE (v0.3 §5.2):** The spec's R-DID MUST requirement — one new unique R-DID per relationship — materially reduces this risk for compliant implementations. However, the M-DID bootstrapping exception (Privacy Considerations §9) creates a residual window: if migration to R-DIDs is never triggered normatively, early-phase M-DID usage remains linkable. | Privacy; Surveillance | Medium | Low | Member's full community participation graph exposed; surveillance by state actors; chilling effect on membership in politically sensitive VTCs. | M-09: ZKP / Selective Disclosure Uptake M-17: Cross-VTC Revocation Contamination Rate | US-04, US-06 | SC-09 | GR-09, GR-06 | CT-15, CT-50 | AT-09, AT-06 | EPIC-9 | ●● Should address
RK-SC01 | Over-Disclosure in IDVC Schema | Schemas | Phase 4 | The IDVC schema requires or permits more personal data than strictly necessary. Excess data increases breach impact and enables cross-system correlation. | Privacy; Data Protection | Medium | Medium | Excessive personal data collected; breach exposes more than necessary; correlation with external databases enables de-anonymisation. | M-09: ZKP / Selective Disclosure Uptake M-04: IDVC Issuer Verification Rate | US-05 | SC-04 | GR-06, GR-09 | CT-16, CT-17 | AT-06, AT-09 | EPIC-4, EPIC-9 | ●● Should address
RK-SC02 | Credential Schema Ambiguity | Schemas | All phases | Underspecified VRC, VMC, or IDVC schemas lead to inconsistent implementation across personal network managers, VTAs, and IDVPs — creating interoperability failures and policy bypass opportunities. **SPEC UPDATE (v0.3 §2–§4):** The spec defines a formal W3C VC type hierarchy and normative base structure (§4), reducing schema ambiguity for the six DTG credential types. However, the DTG JSON-LD context (`firstperson.network/credentials/dtg/v1`) is not yet published as a resolvable normative artefact, and no conformance test suite exists. Schema ambiguity risk is partially reduced but not resolved. | Technical Failure; Governance Failure | Medium | Medium | VTA rejects valid credentials due to schema mismatch; non-compliant implementations admit members who should be rejected; community trust damaged. | M-04: IDVC Issuer Verification Rate M-15: DID Document Integrity Verification Rate | US-01, US-05, US-07 | SC-01, SC-04 | GR-01 | CT-18, CT-19 | AT-01 | EPIC-1, EPIC-4, EPIC-13 | ●● Should address
RK-NM01 | Personal Network Manager UX Failure | Network Managers | All phases | The personal network manager presents cryptographic operations incomprehensibly to non-technical members, causing errors, abandonment, or security failures. The DTGWG itself acknowledges UX as 'the single hardest problem'. | Human Experience; Usability; Security | High | High | Members generate unsafe keys; incorrect M-DID selection creates linkability; members abandon onboarding; trust task ceremonies not completed correctly. | M-12: Member Admission Denial Rate M-03: VRC Reciprocity Rate | US-01, US-02, US-03, US-04 | SC-01, SC-02, SC-03, SC-04 | GR-06 | CT-20, CT-21 | AT-06 | EPIC-12 | ●●● Must address
RK-NM02 | Key Loss / Recovery Failure | Network Managers | All phases | A member loses access to their M-DID private key with no recovery mechanism, rendering their membership credential unverifiable and participation irrecoverable. | Service Disruption; Human Experience | Medium | Medium | Member locked out permanently; trust graph has orphaned nodes; key recovery attempts create identity fraud risk if not properly gated. | M-13: Credential Expiry-to-Renewal Latency | US-03, US-04 | SC-03, SC-04 | GR-01 | CT-22 | AT-01 | EPIC-12, EPIC-13 | ●● Should address
RK-CR01 | Credential Revocation Without Due Process | Credentials | Revocation | A VMC is revoked without prior notice, documented rationale, or accessible appeals. May be triggered by anchor pressure, administrative error, or deliberate abuse. | Human Rights; Governance Failure | High | Medium | Member unjustly excluded; professional or reputational harm; no remedy available; chilling effect on participation for other members. | M-02: Time to Revocation Notice (SLA) M-07: Appeals Process Response Time M-09: ZKP / Selective Disclosure Uptake | US-06 | SC-06 | GR-08, GR-09 | CT-23, CT-24 | AT-08, AT-09 | EPIC-5, EPIC-11 | ●●● Must address
RK-CR02 | Stale Credential / Expiry Without Renewal Path | Credentials | Revocation | VTC credentials expire without a clear, accessible renewal pathway. Members unable to renew lose membership inadvertently. | Service Disruption; Human Experience | Medium | Medium | Active members locked out through administrative failure; valuable contributors excluded; trust in credential infrastructure eroded. | M-13: Credential Expiry-to-Renewal Latency M-02: Time to Revocation Notice (SLA) | US-05, US-06 | SC-05 | GR-08 | CT-25 | AT-08 | EPIC-5 | ●● Should address
RK-CR03 | Revocation Cascade / Cross-VTC Contamination | Credentials | Revocation | Revocation in one VTC propagates to credentials in other unrelated VTCs, or revocation status becomes globally visible. | Privacy; Human Rights | Medium | Low | Member penalised across multiple communities for a single community's decision; effective blacklisting without cross-community due process. | M-17: Cross-VTC Revocation Contamination Rate M-09: ZKP / Selective Disclosure Uptake | US-06 | SC-06 | GR-09 | CT-26 | AT-09 | EPIC-5, EPIC-9 | ●● Should address
RK-CY01 | ZKP Implementation Failure | Cryptography | Phase 4 / Revocation | Zero-knowledge proof implementations for privacy-preserving IDVC presentation or revocation are incorrectly implemented, introducing soundness or zero-knowledge property failures. | Privacy; Security; Technical Failure | High | Low | Member identity data exposed despite expectation of privacy; forged ZKP proofs used to pass admission checks with invalid credentials. | M-09: ZKP / Selective Disclosure Uptake M-15: DID Document Integrity Verification Rate | US-04, US-05 | SC-04 | GR-06, GR-07 | CT-27, CT-28 | AT-06, AT-07 | EPIC-9, EPIC-7 | ●●● Must address
RK-CY02 | Quantum / Algorithm Obsolescence | Cryptography | Long-term | Cryptographic algorithms underpinning VTC credentials become vulnerable to quantum computing attacks or are deprecated, requiring coordinated migration of all community credentials. **SPEC UPDATE (v0.3 §9):** The spec's format-agnostic ZKP design — explicitly not binding to BBS+, SD-JWT-VC, or any specific scheme — reduces algorithm lock-in and partially supports algorithm agility (CT-29). The spec does not yet define a migration pathway or post-quantum readiness assessment requirement. | Security; Technical Failure | Medium | Low | All existing credentials become cryptographically untrustworthy; mass re-issuance required; members without updated tooling excluded during transition. | M-15: DID Document Integrity Verification Rate M-16: Governance Response Time to Security Findings | US-07 | SC-08 | GR-16, GR-17 | CT-29 | AT-16, AT-17 | EPIC-7, EPIC-8 | ●● Should address
RK-AI01 | Agent Credential Scope Creep | AI Agents | Agent Lifecycle | An AI agent exceeds the cryptographic capability constraints in its delegation credential through misconfiguration, vulnerability, or adversarial prompt injection. | Security; Trust Graph Integrity | High | Medium | Agent performs unauthorised credential operations; if compromised, attacker gains persistent trusted access with full operator permissions. | M-08: Agent Credential Scope Violation Rate M-18: Rate-Limiting Trigger Accuracy (AI/NHI) | US-08, US-09 | SC-10, SC-11 | GR-12, GR-13 | CT-30, CT-31 | AT-12, AT-13 | EPIC-6, EPIC-7 | ●●● Must address
RK-AI02 | Stale Agent After Operator Revocation | AI Agents | Agent Lifecycle | An AI agent continues to operate and present credentials after its human operator's VMC has been revoked, because revocation does not propagate to the agent credential. | Security; Trust Graph Integrity | High | Medium | Revoked member's agent maintains unauthorised VTC access; governance decisions may be influenced by a member no longer legitimate. | M-08: Agent Credential Scope Violation Rate M-13: Credential Expiry-to-Renewal Latency | US-08 | SC-10 | GR-12 | CT-32 | AT-12 | EPIC-6 | ●●● Must address
RK-AI03 | AI-Mediated Sybil Generation at Scale | AI Agents | Phase 4 / Agent Lifecycle | A malicious actor deploys AI agents to automate synthetic identity creation and coordinated VRC vouching at a speed that overwhelms human review capacity and defeats standard rate-limiting. | Identity Fraud; Trust Graph Integrity | High | Medium | VTC trust graph flooded with synthetic members; governance capture by AI-controlled fake identities; admission controls rendered ineffective. | M-14: Sybil Cluster Detection Rate M-18: Rate-Limiting Trigger Accuracy (AI/NHI) | US-09, US-10 | SC-11, SC-07 | GR-14, GR-07 | CT-33, CT-34 | AT-14, AT-07 | EPIC-6, EPIC-7, EPIC-8 | ●●● Must address
RK-AI04 | LLM-Powered Social Engineering of Anchors | AI Agents | Phase 2–3 | Adversarial AI agents generate convincing synthetic communications to social-engineer community trust anchors into issuing VRCs or invitation credentials to fraudulent applicants. **SPEC UPDATE (v0.3 §7.3):** The Witness Credential (VWC) provides a partial technical counter-measure: requiring a VWC from a trusted in-person or out-of-band witness for high-stakes anchor-level VRCs makes AI-generated synthetic personas harder to sustain. This does not eliminate the risk but raises the operational cost of the attack. | Identity Fraud; Social Engineering | High | Medium | Fraudulent members admitted through compromised anchor vouching; anchor reputation and liability implicated; trust graph integrity undermined. | M-05: Anomaly Detection Hit Rate (Vouching) M-18: Rate-Limiting Trigger Accuracy (AI/NHI) | US-03, US-09 | SC-11 | GR-14 | CT-35, CT-36, CT-54 | AT-14 | EPIC-6, EPIC-2 | ●●● Must address
RK-EX01 | State-Level Coercion of Anchors / IDVPs | External | Ongoing | A government agency legally compels trust anchors, IDVPs, or registry operators to disclose member identities, revoke credentials for political purposes, or grant unauthorised write access. | Privacy; Political Repression; Human Rights | High | Medium | Dissidents identified and targeted via VTC membership data; members forced out under political pressure; VTC becomes instrument of state surveillance. | M-06: Registry Write Auth Failure Rate M-10: Jurisdictional Concentration | US-11 | SC-09 | GR-11, GR-10 | CT-37, CT-38 | AT-11, AT-10 | EPIC-13, EPIC-7 | ●●● Must address
RK-EX02 | Registry Censorship / Denial of Service | External | Ongoing | A state actor or adversary blocks access to the VTC trust registry or VTA, preventing credential verification and collapsing VTC operations. | Service Disruption; Political Repression | Medium | Medium | VTC operations halted; members unable to verify credentials or be admitted; VTA unavailability cascades to relying parties. | M-06: Registry Write Auth Failure Rate M-15: DID Document Integrity Verification Rate | US-07, US-11 | SC-08, SC-09 | GR-10, GR-16 | CT-39 | AT-10, AT-16 | EPIC-7, EPIC-13 | ●● Should address
RK-EX03 | Legal / Regulatory Framework Conflict | External | All phases | VTC operations or credential schemes conflict with applicable data protection law (GDPR, eIDAS 2.0) or national identity law, exposing the governing body to liability. | Legal / Regulatory | Medium | Medium | Governing body exposed to regulatory fines; members' data processed unlawfully; IDVP faces licence revocation; VTC forced to suspend operations. | M-09: ZKP / Selective Disclosure Uptake M-04: IDVC Issuer Verification Rate | US-01, US-05 | SC-01, SC-04 | GR-06, GR-09, GR-17 | CT-40, CT-41 | AT-06, AT-09, AT-17 | EPIC-9, EPIC-13 | ●● Should address
RK-HX01 | Chilling Effect on Community Participation | Human Experience | All phases | Members self-censor or reduce participation because VTC membership, credential graph, or communications are observable by governance bodies or adversaries. | Human Rights; Privacy; Community Health | Medium | Medium | Community loses diversity and candour; whistle-blowers and dissidents avoid participation; community loses the genuine peer relationship value that DTG is designed to enable. | M-09: ZKP / Selective Disclosure Uptake M-12: Member Admission Denial Rate | US-04, US-06 | SC-09 | GR-09, GR-06 | CT-15, CT-42 | AT-09, AT-06 | EPIC-9, EPIC-10 | ●● Should address
RK-HX02 | Discriminatory Vouching Practices | Human Experience | Phase 2–4 | Trust anchors or members informally apply discriminatory criteria when vouching, perpetuating social biases even when formal admission criteria are non-discriminatory. | Discrimination; Exclusion | High | Medium | Marginalised groups excluded through informal practices; VTC replicates existing social inequalities; legal exposure for governing body. | M-12: Member Admission Denial Rate M-05: Anomaly Detection Hit Rate (Vouching) | US-03, US-04 | SC-03 | GR-03, GR-06 | CT-10, CT-43 | AT-03, AT-06 | EPIC-10, EPIC-2 | ●●● Must address
RK-HX03 | Reputational Harm from Public Revocation | Human Experience | Revocation | A member's revocation status is disclosed publicly in a way that damages their professional or personal reputation, even if the revocation was erroneous or later overturned. | Reputational Harm; Human Rights | High | Medium | Member suffers professional consequences before appeal is resolved; reputational harm not remedied even if appeal succeeds; chilling effect on participation for others. | M-02: Time to Revocation Notice (SLA) M-17: Cross-VTC Revocation Contamination Rate | US-06 | SC-06 | GR-08, GR-09 | CT-24, CT-44 | AT-08, AT-09 | EPIC-5, EPIC-11 | ●●● Must address
RK-SY01 | Trust Graph Capture by Coordinated Actor | Systemic | Phase 3–4 / Ongoing | A coordinated adversary — through Sybil attacks, anchor collusion, or gradual infiltration — gains sufficient influence to control admission decisions, governance votes, or community norms. | Trust Graph Integrity; Governance Failure | High | Medium | VTC governance captured by malicious actors; legitimate members outvoted or silenced; community used as infrastructure for further attacks; DTG ecosystem integrity undermined. | M-01: Anchor Diversity Index M-05: Anomaly Detection Hit Rate (Vouching) M-14: Sybil Cluster Detection Rate | US-10, US-09 | SC-07, SC-11 | GR-03, GR-07, GR-10, GR-14 | CT-04, CT-09, CT-34, CT-45 | AT-03, AT-07, AT-10, AT-14 | EPIC-7, EPIC-8 | ●●● Must address
RK-SY02 | Coordinated Inauthentic Behaviour (CIB) in Governance | Systemic | Ongoing | A coordinated disinformation network exploits governance mechanisms to undermine anchor reputations, exhaust governance bandwidth, and fragment community consensus. | Governance Failure; Community Harm | High | Medium | Trust anchors resign or make poor decisions under attack; governance bandwidth consumed; VTC unable to function as intended. | M-11: Bad-Faith Appeals Rate M-05: Anomaly Detection Hit Rate (Vouching) | US-12 | SC-12 | GR-15, GR-16 | CT-07, CT-46 | AT-15, AT-16 | EPIC-11, EPIC-7 | ●●● Must address
RK-SY03 | Open Issues Left Unresolved at Scale | Systemic | Phase 4 / Long-term | The four open issues in the VTC Bootstrapping Draft — uniqueness, trust task protocols, expiration/revocation, DID document storage — remain unresolved when the VTC scales beyond small community management. | Technical Failure; Governance Failure | High | High | Uniqueness enforcement fails at scale; revocation mechanisms fail under load; DID documents become irresolvable; trust task protocols incompatible across implementations. | M-14: Sybil Cluster Detection Rate M-16: Governance Response Time to Security Findings | US-07 | SC-07, SC-08 | GR-07, GR-17 | CT-47, CT-48 | AT-07, AT-17 | EPIC-7, EPIC-8, EPIC-13 | ●●● Must address
RK-SC03 | VRC Over-Disclosure — Rich Data in Core Edge | Schemas | All phases | The VRC schema (spec §5.2) requires only the target DID and proof, but places no constraint on what additional data may be embedded in `credentialSubject`. Implementers who embed rich relationship metadata — relationship duration, first-meeting location, mutual endorsements — directly in VRCs rather than using the annotation credential layer (VPC, VEC, VWC) create credentials in which both parties have cryptographically committed to that data. It cannot then be selectively disclosed or withheld from verifiers. The annotation credential architecture exists in the spec but is not normatively required as the channel for supplementary data. **Introduced by:** DTG Credential Spec v0.3 analysis (RAHP commentary §2.4). | Privacy; Data Protection | Medium | Medium | Members inadvertently commit to more personal data than intended in bilateral VRCs; ZKP selective disclosure is undermined because the data is in the core credential, not an annotation; relationship graphs become richer surveillance targets than necessary. | M-09: ZKP / Selective Disclosure Uptake | US-04, US-06 | SC-03, SC-04 | GR-06, GR-09 | CT-49 | AT-06, AT-09 | EPIC-9, EPIC-12 | ●● Should address
RK-SC04 | M-DID Bootstrapping Exception Undermines R-DID Privacy | Schemas | Phase 1–3 | Spec §5.2 permits M-DIDs 'for bootstrapping' with no normative migration trigger or timeline. The Privacy Considerations section (§9) recommends migration to R-DIDs post-bootstrapping but does not make this a normative requirement. In practice, if migration never happens — the likely outcome without a phase-gate — early VRC relationships remain M-DID-based. An adversary monitoring the trust registry during the bootstrapping phase can reconstruct membership graphs from M-DID co-occurrences in VRCs issued before migration. **Introduced by:** DTG Credential Spec v0.3 §5.2 and Privacy Considerations §9 (RAHP commentary §2.5). | Privacy; Governance Failure | Medium | High | The R-DID architecture's privacy guarantee is contingent on migration actually happening. Without a normative trigger, the bootstrapping exception becomes the permanent operating mode for many implementations. State actors and registry observers can reconstruct trust graphs from the pre-migration VRC corpus. | M-09: ZKP / Selective Disclosure Uptake M-17: Cross-VTC Revocation Contamination Rate | US-04, US-06, US-11 | SC-01, SC-02, SC-09 | GR-18 | CT-50 | AT-18 | EPIC-9, EPIC-13 | ●●● Must address
RK-CR04 | Endorsement Credential (VEC) Manipulation | Credentials | Phase 3–4 / Ongoing | Spec §7.2 defines the VEC's `endorsement` field as 'community/VTN-defined — structure and fields determined by community policy.' This maximum flexibility, with no normative constraint requiring endorsers to be co-members of the same VTC as the endorsed party, creates a reputation manipulation attack surface. A coordinated bad-faith actor can issue large volumes of fabricated VECs with high `competencyLevel` claims to inflate the reputation of synthetic personas, then use those reputational signals to gain governance influence. **Introduced by:** DTG Credential Spec v0.3 §7.2 (RAHP commentary §2.8). | Governance Failure; Identity Fraud | Medium | Medium | Synthetic personas receive artificially inflated reputation scores via coordinated VEC issuance; governance decisions influenced by reputational signals that are manufactured rather than earned; admission thresholds gamed via endorsement proxies. | M-05: Anomaly Detection Hit Rate (Vouching) M-14: Sybil Cluster Detection Rate | US-03, US-10, US-12 | SC-07, SC-12 | GR-03 | CT-55 | AT-03 | EPIC-2, EPIC-7, EPIC-11 | ●● Should address
RK-G05 | Governanceless VTC Claiming Credential Compliance | Governance | Phase 1 | The DTG Credential Specification v0.3 defines credential schemas (§2–§8) and normative credential requirements without requiring that a VTC deploying these credentials has any governance framework in place. A developer group could deploy technically compliant VMCs and VRCs — passing all credential-layer verification checks — while operating with no genesis policy, no time-bounded initiator authority, and no trust anchor diversity requirements. Relying parties would have no normative signal that governance is absent. **Introduced by:** DTG Credential Spec v0.3 analysis — gap identified in §9 (Trust Registries section) and commentary §2.9. | Governance Failure; False Assurance | Medium | High | Relying parties accept VMCs from VTCs with no governance backing; DTG compliance signals trustworthiness that does not exist at the governance layer; a single actor controls a 'compliant' VTC indefinitely with no accountability. | M-01: Anchor Diversity Index M-16: Governance Response Time to Security Findings | US-01, US-04 | SC-01 | GR-01, GR-02 | CT-56 | AT-01, AT-02 | EPIC-1, EPIC-13 | ●●● Must address

## Controls Catalogue
DTG RAHP – Controls Catalogue ¦ CT-01–CT-48 ¦ Risk-reducing measures (NOT phase gates — see Guardrails sheet for phase gates)
Control Types: Technical · Governance · Procedural · UX · Legal ¦ Standards Relevance: High = normative candidate · Medium = recommended · Low = best practice
Control ID | Control Name | Type | Description | Linked Guardrail (if underpins one) | Linked Risk IDs | Standards Relevance | Priority Rationale
CT-01 | Version-Controlled Public Genesis Policy | Procedural | All Phase 1 bootstrapping policies must be committed to a public, version-controlled record before Phase 2 begins. This creates an auditable baseline for community governance. | GR-01 | RK-G01 | High
CT-02 | Independent Governance Review at Genesis | Governance | An independent review of bootstrap policies by parties other than the initiator must be completed before the VTC admits non-initiator members. Reviewer identity and findings to be recorded. | — | RK-G01 | High
CT-03 | Governance Transition Milestones | Governance | Explicit milestones for transitioning initiator authority to the governing body must be defined and documented before Phase 2. The VTA PEP enforces authority expiry at the documented milestone. | GR-02 | RK-G02 | High
CT-04 | Trust Anchor Diversity Policy | Governance | A minimum diversity standard for trust anchors — geographic, organisational, cultural — must be defined and enforced before Phase 2 seeding. Homogeneous anchor clusters constitute a policy violation. | GR-03 | RK-G03, RK-SY01 | High
CT-05 | Anchor Clustering Metric Monitoring | Technical | The VTA tracks an anchor clustering metric (e.g. organisational or jurisdictional Herfindahl index). Breaches of the diversity floor trigger a governance alert before additional anchors are admitted. | — | RK-G03 | Medium
CT-06 | Governance Capacity Planning | Procedural | The governing body must conduct annual capacity planning for admission, appeals, revocation, and security incident workloads, including adversarial load scenarios. | — | RK-G04 | Medium
CT-07 | Complaint / Appeals Rate-Limiting | Technical | The VTA or governance portal enforces rate-limiting on complaint and appeal submissions per member per time period, without suppressing legitimate single-member grievances. | GR-15 | RK-G04, RK-SY02 | High
CT-08 | Uniqueness Enforcement Mechanism | Technical | A documented uniqueness enforcement mechanism must be in place before Phase 4 opens. Acceptable approaches include ZKP personhood proofs, trusted IDVP attestation, or social recovery quorum. Absence must be formally risk-accepted. | GR-07 | RK-ID01, RK-AI03, RK-SY03 | High
CT-09 | Vouching Pattern Anomaly Detection | Technical | The VTA or a monitoring layer analyses vouching patterns for statistical anomalies — e.g. tight clusters of mutual vouching from a small group — and triggers governance review when thresholds are breached. | — | RK-ID01, RK-SY01 | High
CT-10 | Non-Discriminatory Admission Criteria | Governance | Admission criteria must be published, non-discriminatory, and reviewed against applicable equality law before Phase 3 opens. Criteria must not create de facto barriers for specific cultural, geographic, or socioeconomic groups. | GR-06 | RK-ID02, RK-HX02 | High
CT-11 | Alternative Identity Proofing Paths | Procedural | At least one admission pathway must not require conventional government-issued ID, to accommodate the estimated 850 million people globally who lack recognised ID documents. Alternative proofing options must be documented in governance. | GR-06 | RK-ID02 | High
CT-12 | IDVP Security Approval Criteria | Governance | IDVPs must meet documented security and operational standards — including breach notification obligations — before being approved and registered in the VTC trust registry. | GR-05 | RK-ID03 | High
CT-13 | IDVP Deregistration Handling Protocol | Procedural | The governing body must define how member VMCs issued via a deregistered IDVP's IDVCs are handled: whether they remain valid, require re-verification, or are revoked. The protocol must include member notification within an agreed SLA. | — | RK-ID03 | High
CT-14 | DID Document Integrity Verification | Technical | The VTA must verify DID document integrity cryptographically before accepting any credential presentation, using tamper-evident registry entries or equivalent mechanism. DID document storage and access requirements must be specified in the credential spec. | GR-10 | RK-ID04 | High
CT-15 | Pseudonymous Per-VTC M-DID Design | Technical | Personal network managers should generate a distinct M-DID per VTC, and registry metadata exposure should be minimised to prevent cross-community profiling. This should be a normative design requirement in the DTG credential specification. | GR-09 | RK-ID05, RK-HX01 | High
CT-16 | Minimum-Necessary IDVC Attribute Set | Governance | A defined minimum-necessary IDVC attribute set must be published before Phase 4, specifying only attributes strictly required by VTC admission policy. DPIA must be completed before IDVC schema is deployed. | GR-06 | RK-SC01 | High
CT-17 | Data Minimisation Audit | Procedural | An annual data minimisation audit of all credential schemas (VRC, VMC, IDVC) must be conducted to identify and remove attributes no longer required by policy. | — | RK-SC01 | Medium
CT-18 | Normative Credential Schema Publication | Technical | Normative credential schemas for VRC, VMC, and IDVC must be published before Phase 2. Schemas must include version identifiers and a backwards-compatibility policy. | GR-01 | RK-SC02 | High
CT-19 | Conformance Test Suite | Technical | A conformance test suite for VTA and personal network manager implementations must be published, enabling automated verification that implementations correctly enforce admission policies and credential schemas. | — | RK-SC02 | High
CT-20 | Sovereign Wallet UX Design Principles | UX | UX design principles for sovereign wallets must be defined, addressing task-based trust ceremonies, plain-language guidance, accessibility (WCAG 2.1 AA minimum), and user testing with non-technical participants before launch. | GR-06 | RK-NM01 | High
CT-21 | Non-Technical User Onboarding Testing | UX | Structured user testing with non-technical participants must be conducted before each major release of the personal network manager, covering the Phase 1–4 trust task ceremonies. | — | RK-NM01 | Medium
CT-22 | Key Recovery Mechanism | Technical | A key recovery mechanism — e.g. social recovery quorum, hardware backup — must be defined and documented in the personal network manager UX. Governance policy for M-DID replacement must cover recovery scenarios. | — | RK-NM02 | High
CT-23 | Mandatory Pre-Revocation Notice | Governance | No VMC shall be revoked without prior written notice to the member, including documented rationale and the available appeals pathway, delivered within an agreed notice period (recommended: minimum 14 days except emergency security revocations). | GR-08 | RK-CR01 | High
CT-24 | Privacy-Preserving Revocation Disclosure | Technical | Revocation status must not be publicly linked to a member's real-world identity by default. ZKP-based status lists (e.g. W3C Status List 2021 with ZKP) or equivalent privacy-preserving mechanisms should be used. | GR-09 | RK-CR01, RK-HX03 | High
CT-25 | Credential Renewal Workflow | Technical | A defined credential renewal workflow — including advance expiry notification (recommended: 30 days) and a grace period — must be implemented before Phase 4. Autonomous agent renewal (US-08) addresses this for agent-managed credentials. | — | RK-CR02 | Medium
CT-26 | VTC-Scoped Revocation | Technical | Revocation must be explicitly scoped to the issuing VTC only. Cross-VTC revocation requires a separate, documented governance decision by each affected VTC's governing body. | GR-09 | RK-CR03 | High
CT-27 | Audited ZKP Library Requirement | Technical | Only ZKP implementations that have undergone formal security review or are from audited open-source libraries may be used in VTC credential workflows. The DTGWG charter identifies ZKP as a major focus area. | GR-06 | RK-CY01 | High
CT-28 | ZKP Conformance Testing | Technical | A conformance test suite for ZKP implementations must be developed as part of the DTG credential specification, covering soundness, completeness, and zero-knowledge properties. | GR-07 | RK-CY01 | High
CT-29 | Algorithm Agility and Migration Pathway | Technical | VTC credential schemas must be designed for algorithm agility. A quantum-readiness assessment and migration pathway must be defined in governance and reviewed at least every two years. | GR-16, GR-17 | RK-CY02 | Medium
CT-30 | Cryptographic Delegation Scope Constraints | Technical | AI agent delegation credentials must cryptographically encode explicit capability constraints (e.g. permitted credential types, target VTCs, time window). The VTA PEP must enforce these constraints and reject out-of-scope operations. | GR-12 | RK-AI01 | High
CT-31 | Short-Lived Agent Credentials | Technical | AI agent delegation credentials should be short-lived (recommended: maximum 24-hour validity) with automated renewal tied to operator membership liveness checks, reducing the window of exposure for compromised agent credentials. | GR-13 | RK-AI01 | High
CT-32 | Agent Liveness Check on Operator VMC | Technical | Before executing any delegated credential operation, an AI agent must verify that its operator's VMC remains valid in the VTC trust registry. Operator revocation must propagate to agent credential invalidation within an agreed SLA (recommended: ≤1 hour). | GR-12 | RK-AI02 | High
CT-33 | Non-Human Activity Rate-Limiting | Technical | The VTA and governance portal must enforce rate-limiting on admission requests, credential presentations, and invitation submissions, calibrated to distinguish human from automated activity patterns. | GR-14 | RK-AI03, RK-AI04 | High
CT-34 | Behavioural Anomaly Detection for Non-Human Actors | Technical | A behavioural anomaly detection layer must be deployed before Phase 4 to identify non-human activity patterns, including high-frequency admission attempts, coordinated vouching, and adversarial policy fuzzing. | GR-14 | RK-AI03, RK-SY01 | High
CT-35 | Anchor Awareness of AI Social Engineering | Procedural | Community trust anchors must receive training on AI-powered social engineering vectors, including LLM-generated synthetic personas. Training must be updated at least annually. | — | RK-AI04 | Medium
CT-36 | Out-of-Band Verification for High-Stakes Vouching | Procedural | For Phase 2 trust anchor admission and Phase 3 high-trust vouching, anchors should use out-of-band verification (e.g. video call, in-person meeting) before issuing VRCs, particularly when requests arrive via digital-only channels. | — | RK-AI04 | Medium
CT-37 | Jurisdictional Diversity of Key Parties | Governance | The governing body must document the jurisdictional distribution of trust anchors and IDVPs, and assess the risk of any single jurisdiction having coercive legal leverage over a controlling majority of key parties. | GR-11 | RK-EX01 | High
CT-38 | Legal Coercion Response Protocol | Procedural | A documented legal coercion response protocol must be in place for trust anchors and IDVPs, including guidance on legal rights, obligations, escalation contacts, and member notification procedures when disclosure orders are received. | — | RK-EX01 | High
CT-39 | Distributed Registry Architecture | Technical | The VTC trust registry must be deployed with geographic redundancy and a defined degraded-mode operation specification, so that VTA unavailability in one region does not collapse VTC operations globally. | GR-10 | RK-EX02 | Medium
CT-40 | Legal Review of Credential Schemas | Legal | A legal review of all credential schemas and trust registry designs against applicable data protection law (GDPR, eIDAS 2.0) must be completed before Phase 4. A DPO (or equivalent) must sign off on IDVC processing. | GR-06 | RK-EX03 | High
CT-41 | Open Issues Regulatory Risk Acceptance | Governance | Each of the four VTC Bootstrapping Draft open issues must have an explicit regulatory risk assessment, and any accepted risks must be formally signed by the governing body with a review date. | GR-17 | RK-EX03 | High
CT-42 | Anonymous Membership Option | Technical | For VTCs operating in politically sensitive contexts, an anonymous membership pathway — using ZKP proofs of valid credentials without linking to real-world identity — should be available. | GR-09 | RK-HX01 | Medium
CT-43 | Governing Body Accountability for Systematic Exclusion | Governance | The governing body must track admission denial rates by demographic proxy where legally permissible, and must have a defined escalation process when systematic exclusion patterns are identified. | — | RK-HX02 | Medium
CT-44 | Remediation Pathway After Overturned Revocation | Governance | Where a revocation is overturned on appeal, a documented remediation pathway must exist, including restoration of credentials, notification to relevant parties, and record correction. | — | RK-HX03 | Medium
CT-45 | Multi-Party Registry Write Authorisation | Technical | Trust registry writes must require multi-party or threshold authorisation (e.g. m-of-n signature). No single actor — including an IDVP, anchor, or registry operator — shall have unilateral write access. All writes must be logged in a tamper-evident audit trail. | GR-10 | RK-SY01, RK-EX01 | High
CT-46 | Coordinated Behaviour Detection in Governance | Technical | The complaints and appeals workflow must include coordinated behaviour detection, identifying statistically anomalous submission patterns (timing, content similarity, source clustering) that indicate organised bad-faith campaigns. | GR-15 | RK-SY02 | Medium
CT-47 | Formal Open Issues Mitigation Plan | Governance | Each of the four VTC Bootstrapping Draft open issues must have a formal mitigation plan with owner, target resolution date, and interim risk controls, signed by the governing body before Phase 4. | GR-17 | RK-SY03 | High
CT-48 | Threat Model Maintenance | Governance | A formal VTC threat model must be published, reviewed, and updated at least annually. It must cover at minimum: Sybil attacks, state coercion, anchor collusion, AI-mediated attacks, registry manipulation, and CIB in governance. | GR-16 | RK-SY03, RK-CY02 | High
CT-49 | VRC Data Minimisation Clause | Technical | The VRC `credentialSubject` SHOULD contain only the minimum claims necessary for graph structure: the target party's DID and the `validFrom` timestamp. Additional relationship metadata (skills, event context, endorsements) SHOULD be expressed through annotation credentials (VPC, VEC, VWC per spec §7) rather than embedded in the VRC itself. Implementations MUST NOT require VRC subjects to include personal data beyond that strictly required by VTC admission policy. **Source:** DTG Credential Spec v0.3 commentary recommendation R6 (§2.4). | GR-06 | RK-SC03, RK-HX01, RK-ID05 | High
CT-50 | M-DID to R-DID Migration Trigger | Governance | VTC implementations MUST define and publish a normative trigger for migration from M-DID-based to R-DID-based VRC edges, as required by spec §5.2 privacy intent. The trigger SHOULD occur before Phase 4 opens or before the VTC exceeds a governance-defined membership threshold. After the trigger, new VRCs MUST use R-DIDs. The migration trigger condition and date MUST be recorded in the trust registry. **Source:** DTG Credential Spec v0.3 §5.2 Privacy Considerations and commentary recommendation R7 (§2.5). | GR-18 | RK-SC04, RK-ID05, RK-HX01 | High
CT-51 | Non-Human DID Designation in DID Document | Technical | Agent DIDs MUST be designated as non-human in the DID Document using a defined service type property or a `@type` assertion, enabling VTAs to apply agent-specific policy. VTAs MAY reject VMC applications from DIDs not carrying a human attestation where VTC policy requires proof of personhood. This creates a normative distinction between Aether (M1) and Phantom (M2) at the DID layer. **Source:** DTG Credential Spec v0.3 analysis — gap in §5.1/§5.2 (commentary §2.3, recommendation R1, §10.1). | GR-12 | RK-AI01, RK-AI03 | High
CT-52 | Agent Delegation Credential Requirement | Technical | An AI agent operating on behalf of a human VTC member MUST hold a delegation credential issued by that member's M-DID, referencing the member's VMC and specifying the agent's permitted capability scope as a normative `credentialSubject` claim. Without this, the spec's VMC schema cannot distinguish an authorised agent (Aether, M1) from an adversarial one (Phantom, M2). **Source:** DTG Credential Spec v0.3 analysis — gap in §5.1 (commentary §2.3, recommendation R1, §10.2). | GR-12 | RK-AI01, RK-AI02 | High
CT-53 | VIC Role Embedding (membershipRole field) | Technical | The VIC `credentialSubject` SHOULD include a `membershipRole` field specifying the role to be granted upon admission (e.g. 'trustAnchor', 'member'). This allows the issuer to cryptographically commit to the intended role at invitation time, enabling offline verification and making the VIC tamper-evident with respect to role assignment — independent of trust registry availability. The spec's open question ('Q: Should any of this be embedded in the VIC?') in §6.1 should be resolved in this direction. **Source:** DTG Credential Spec v0.3 §6.1 open question (commentary recommendation R4, §2.6). | GR-01 | RK-G01, RK-SC02 | High
CT-54 | VWC Requirement for High-Stakes Anchor Admission | Technical | For Phase 2 trust anchor admission, VTC governance SHOULD require that VRCs used in anchor admission packages be accompanied by a Witness Credential (VWC per spec §7.3) from a trusted third party attesting to the in-person or verified out-of-band nature of the relationship. This directly implements CT-36 (Out-of-Band Verification) using the VWC schema and raises the cost of AI-generated synthetic anchor persona attacks (RK-AI04). The VWC `witnessContext.method` field should record the verification method. **Source:** DTG Credential Spec v0.3 §7.3 (commentary §1.4, recommendation R9). | GR-14 | RK-AI04, RK-ID01 | High
CT-55 | VEC Issuer Co-Membership Requirement | Governance | VTC implementations SHOULD require that Endorsement Credential (VEC per spec §7.2) issuers hold a valid VMC from the same C-DID as the endorsed party. VTA policy enforcement points SHOULD verify this co-membership before treating VEC-based reputation signals as valid inputs to admission or governance decisions. Aggregated VEC metrics SHOULD be treated with appropriate scepticism where endorsements form tight clusters from a small issuer group. **Source:** DTG Credential Spec v0.3 §7.2 — underspecification identified in commentary §2.8, recommendation R10. | GR-03 | RK-CR04, RK-SY02 | Medium
CT-56 | VTC Governance Conformance Class | Governance | A VTC claiming DTG credential specification compliance MUST publish a version-controlled governance framework satisfying the requirements of the DTG VTC Governance Specification (forthcoming). At minimum this must include: a genesis policy record (GR-01), a time-bounded initiator authority mechanism (GR-02), and a trust anchor diversity policy (GR-03). The trust registry entry for a DTG-compliant VTC SHOULD include a resolvable reference to its published governance framework. Without this, technical credential compliance provides false assurance to relying parties. **Source:** DTG Credential Spec v0.3 §9 (Trust Registries) — gap identified in commentary §2.9, recommendation R8. | GR-01 | RK-G05, RK-G01, RK-G02 | High

## Guardrails Register
DTG RAHP – Guardrails Register ¦ GR-01–GR-17 ¦ Non-negotiable phase-gate pre-conditions (distinct from controls)
A Guardrail is a binary pass/fail pre-condition that must be satisfied before a phase opens or a capability is activated. Failure to meet a guardrail must block progress, not merely trigger risk-reduction.
Guardrail ID | Guardrail Name | Category | Description / Requirement | Applies to Phase | Owner | Risks Addressed | Underpinning Controls | Assurance Test
GR-01 | Genesis Policy Documentation | Governance | All Phase 1 bootstrapping policies must be version-controlled, publicly readable, and committed to an auditable record before the initiator issues any Phase 2 invitations. Hard-coded policy changes require documented governance approval. | Phase 1 (all subsequent phases) | Initiator / Governing Body | RK-G01, RK-SC02, RK-NM02 | CT-01, CT-18 | AT-01
GR-02 | Time-Bounded Initiator Authority | Governance | Initiator authority must be explicitly time-bounded or role-transitioned under documented governance rules. The VTA PEP must enforce the initiator count limit and refuse Phase 2 actions after authority expiry. | Phase 1–2 | VTA PEP / Governing Body | RK-G01, RK-G02 | CT-03 | AT-02
GR-03 | Trust Anchor Diversity Policy | Governance / Human Experience | A minimum diversity standard for trust anchors must be defined and documented before Phase 2 seeding. The VTA must enforce the anchor count limit. Homogeneous anchor clusters constitute a policy violation. | Phase 2 | Governing Body | RK-G03, RK-HX02, RK-SY01 | CT-04, CT-05 | AT-03
GR-04 | Reciprocal VRC Requirement | Technology / Governance | No VMC shall be issued to a trust anchor or member without a verified reciprocal VRC exchange. The VTA PEP must reject VMC issuance where only a unilateral VRC exists. | Phase 2–4 | VTA PEP | RK-ID01 | CT-08 | AT-04
GR-05 | IDVP Registry Standing | Technology / Governance | IDVCs are only valid for VTC admission if issued by an IDVP whose DID is listed in the VTC trust registry with the role of identity verification provider at the time of presentation. | Phase 4 | VTA PEP / Governing Body | RK-ID03 | CT-12 | AT-05
GR-06 | Privacy-Preserving Proofing Option | Human Experience / Technology | At least one privacy-preserving alternative to raw IDVC disclosure (ZKP, selective disclosure) must be available for Phase 4 admission. No applicant should be required to disclose more data than strictly necessary. | Phase 4 | VTA PEP / DPO | RK-ID02, RK-ID05, RK-SC01, RK-NM01, RK-CY01, RK-EX03, RK-HX01, RK-HX02 | CT-10, CT-11, CT-15, CT-16, CT-20, CT-27, CT-40 | AT-06
GR-07 | Uniqueness Enforcement Mechanism | Technology / Governance | The VTC must define and document its uniqueness enforcement mechanism before Phase 4 opens. Absence of a uniqueness mechanism at scale is an open issue and constitutes a known risk that must be risk-accepted or mitigated. | Phase 4 (open issue) | Governing Body / Security | RK-ID01, RK-CY01, RK-AI03, RK-SY01, RK-SY03 | CT-08, CT-28 | AT-07
GR-08 | Revocation Due Process | Governance / Human Experience | No VMC shall be revoked without prior notice to the member, a documented rationale, and access to a formal appeals process with defined timelines. Revocation criteria must be published in the governance framework. | Revocation | Governing Body / VTA | RK-G04, RK-CR01, RK-CR02, RK-HX03 | CT-23, CT-25 | AT-08
GR-09 | Privacy-Preserving Revocation Disclosure | Technology / Governance | Revocation status must not be publicly linked to member real-world identity by default. ZKP-based or status-list approaches should be used. Cross-VTC contamination must be explicitly scoped and documented. | Revocation | VTA PEP / DPO | RK-ID03, RK-ID05, RK-SC01, RK-CR01, RK-CR03, RK-EX03, RK-HX01, RK-HX03 | CT-15, CT-24, CT-26, CT-42 | AT-09
GR-10 | Multi-Party Registry Write Authorisation | Technology / Governance | Trust registry writes must require multi-party or threshold authorisation. No single actor shall have unilateral write access. All registry writes must be logged in a tamper-evident audit trail. | All phases | Registry Operator / Governing Body | RK-ID04, RK-EX01, RK-EX02, RK-SY01 | CT-14, CT-45 | AT-10
GR-11 | Jurisdictional Diversity for Key Parties | Governance | The VTC governance framework must document the jurisdictional distribution of trust anchors and IDVPs, and assess the risk of any single jurisdiction having coercive legal leverage over a controlling majority of key parties. | Phase 2–4 (ongoing) | Governing Body | RK-G03, RK-EX01 | CT-37 | AT-11
GR-12 | Agent Delegation Scope Constraint | Technology / Governance | AI agents operating on behalf of VTC members must hold cryptographically scoped delegation credentials with explicit capability constraints. Operator revocation of a VMC must propagate to agent credential invalidation within an agreed latency SLA. | Agent Lifecycle | VTA PEP / Operator | RK-AI01, RK-AI02 | CT-30, CT-31, CT-32 | AT-12
GR-13 | Agent Audit Logging | Technology / Governance | All credential operations performed by an AI agent must be logged with sufficient detail to distinguish them from human operations, including agent DID, delegation credential reference, timestamp, and action type. | Agent Lifecycle | VTA / Operator | RK-AI01 | CT-31 | AT-13
GR-14 | Non-Human Actor Detection | Technology / Governance | Rate-limiting and behavioural anomaly detection for non-human activity patterns must be in place before Phase 4 opens. Governance rules must explicitly address agent-mediated attacks. | Phase 4 + Agent Lifecycle | Security / Governing Body | RK-AI03, RK-AI04, RK-SY01 | CT-33, CT-34 | AT-14
GR-15 | Complaint and Appeals Rate-Limiting | Governance / Human Experience | The complaints and appeals process must include rate-limiting controls to prevent bad-faith flooding, without suppressing legitimate grievances. Anti-retaliation protections for legitimate complainants must be documented. | Governance Operations | Governing Body | RK-G04, RK-SY02 | CT-07, CT-46 | AT-15
GR-16 | Formal Threat Model Publication | Governance | A formal VTC threat model covering Sybil attacks, state coercion, anchor collusion, AI-mediated attacks, registry manipulation, and CIB must be published and reviewed before Phase 4 opens and at least annually thereafter. | Pre-Phase 4 / Ongoing | Security / Governing Body | RK-CY02, RK-EX02, RK-SY02 | CT-48 | AT-16
GR-17 | Open Issues Risk Acceptance | Governance | The four open issues from the VTC Bootstrapping Draft — uniqueness, trust task protocols, expiration/revocation, DID document storage — must each be either mitigated or formally risk-accepted by the governing body before Phase 4 opens. | Phase 4 (pre-condition) | Governing Body | RK-CY02, RK-EX03, RK-SY03 | CT-41, CT-47 | AT-17
GR-18 | R-DID Migration Phase Gate | Technology / Governance | Before Phase 4 opens (or before the VTC exceeds a governance-defined membership threshold, whichever comes first), the VTC MUST complete migration from M-DID-based to R-DID-based VRC edges, or formally risk-accept the residual linkability exposure with a documented rationale and review date. The migration trigger MUST be recorded in the trust registry. New VRCs issued after the trigger MUST use R-DIDs. This guardrail converts the spec's §5.2 privacy RECOMMENDATION ('migration recommended post-bootstrapping') into a binding phase gate, closing the residual window identified in RK-SC04. **Source:** DTG Credential Spec v0.3 §5.2 Privacy Considerations. | Pre-Phase 4 | VTA PEP / Governing Body | RK-SC04, RK-ID05, RK-HX01 | CT-50 | AT-18

## Assurance Tests
DTG RAHP – Assurance Tests ¦ AT-01–AT-17 ¦ Binary pass/fail evidence that each Guardrail is met
AT ID | Linked Guardrail | Pass Criterion | Verification Method | Test Type | Risks Covered | Notes
AT-01 | GR-01 | Genesis policy artefact exists, is version-controlled, and was committed before any Phase 2 invitation was issued | Verify via audit trail timestamp comparison — automated | Governance | RK-G01, RK-SC02, RK-NM02
AT-02 | GR-02 | VTA PEP rejects Phase 2 invitation attempts after documented initiator authority expiry | Automated test on VTA PEP | Technology | RK-G01, RK-G02
AT-03 | GR-03 | Anchor diversity metric (geographic / organisational spread) meets documented policy floor at end of Phase 2 | Manual governance audit + VTA metric report | Governance | RK-G03, RK-HX02, RK-SY01
AT-04 | GR-04 | VMC issuance fails when only one-directional VRC exists | VTA PEP automated rejection test | Technology | RK-ID01
AT-05 | GR-05 | IDVP DID not in trust registry with correct role → VTA rejects IDVC presentation | Automated test | Technology | RK-ID03
AT-06 | GR-06 | At least one ZKP / selective disclosure path is available and functional in Phase 4 UX | End-to-end flow test + UX accessibility review | Technology / UX | RK-ID02, RK-ID05, RK-SC01, RK-NM01, RK-CY01, RK-EX03, RK-HX01, RK-HX02
AT-07 | GR-07 | Uniqueness enforcement mechanism is documented; if none exists, risk acceptance is signed and dated | Governance audit — manual | Governance | RK-ID01, RK-CY01, RK-AI03, RK-SY01, RK-SY03
AT-08 | GR-08 | Revocation notice delivered to member within SLA; appeals path accessible within 24 hours | Governance audit + SLA measurement test | Governance | RK-G04, RK-CR01, RK-CR02, RK-HX03
AT-09 | GR-09 | Default revocation status disclosure does not expose member real-world identity | Privacy audit — manual | Governance / Privacy | RK-ID03, RK-ID05, RK-SC01, RK-CR01, RK-CR03, RK-EX03, RK-HX01, RK-HX03
AT-10 | GR-10 | Registry write with single-party authorisation rejected | Automated test on registry API | Technology | RK-ID04, RK-EX01, RK-EX02, RK-SY01
AT-11 | GR-11 | Jurisdictional distribution of key parties documented; coercion risk assessment signed by governing body | Governance audit — manual | Governance | RK-G03, RK-EX01
AT-12 | GR-12 | Agent exceeding capability constraints rejected by VTA PEP; operator VMC revocation propagates to agent within SLA | Automated test + SLA measurement | Technology | RK-AI01, RK-AI02
AT-13 | GR-13 | Agent credential operations visible in operator audit log with all required fields | Log completeness automated test | Technology | RK-AI01
AT-14 | GR-14 | Rate-limiting triggers on high-frequency non-human credential presentation; legitimate agent traffic not false-positively blocked | Load test + false-positive measurement | Technology | RK-AI03, RK-AI04, RK-SY01
AT-15 | GR-15 | Complaint rate-limiting active; legitimate single-member complaint receives response within SLA | Governance audit + SLA measurement | Governance | RK-G04, RK-SY02
AT-16 | GR-16 | Published threat model exists, is dated within 12 months, and covers all six listed threat categories | Governance audit — manual | Governance | RK-CY02, RK-EX02, RK-SY02
AT-17 | GR-17 | All four open issues have documented mitigations or risk acceptances signed by governing body with review dates | Governance audit — manual | Governance | RK-CY02, RK-EX03, RK-SY03
AT-18 | GR-18 | VTC trust registry records a migration trigger date for R-DID adoption; all VRCs issued after that date use R-DIDs (not M-DIDs); OR a formal risk acceptance document is signed by the governing body with rationale and review date, committed to the version-controlled governance record before Phase 4 opens | Governance audit of trust registry migration flag + sample VRC inspection | Governance / Technology | RK-SC04, RK-ID05 | Source: DTG Credential Spec v0.3 §5.2 Privacy Considerations

## Pivot Risk x Controls
DTG RAHP – Pivot: Risk × Guardrails (GR) and Controls (CT) ¦ Read across a row to see all mitigations for a risk ¦ Read down a column to see all risks a control addresses
● = Linked ¦ Orange columns = Guardrails (phase gates) ¦ Green columns = Controls (risk-reducing) ¦ Risks sorted by severity then category
Risk ID | Risk Name | Sev | GR-01 | GR-02 | GR-03 | GR-04 | GR-05 | GR-06 | GR-07 | GR-08 | GR-09 | GR-10 | GR-11 | GR-12 | GR-13 | GR-14 | GR-15 | GR-16 | GR-17 | CT-01 | CT-02 | CT-03 | CT-04 | CT-05 | CT-06 | CT-07 | CT-08 | CT-09 | CT-10 | CT-11 | CT-12 | CT-13 | CT-14 | CT-15 | CT-16 | CT-17 | CT-18 | CT-19 | CT-20 | CT-21 | CT-22 | CT-23 | CT-24 | CT-25 | CT-26 | CT-27 | CT-28 | CT-29 | CT-30 | CT-31 | CT-32 | CT-33 | CT-34 | CT-35 | CT-36 | CT-37 | CT-38 | CT-39 | CT-40 | CT-41 | CT-42 | CT-43 | CT-44 | CT-45 | CT-46 | CT-47 | CT-48
RK-AI01 | Agent Credential Scope Creep | H | [11 empty] | ● | ● | [33 empty] | ● | ●
RK-AI02 | Stale Agent After Operator Revocation | H | [11 empty] | ● | [36 empty] | ●
RK-AI03 | AI-Mediated Sybil Generation at Scale | H | [6 empty] | ● | [6 empty] | ● | [35 empty] | ● | ●
RK-AI04 | LLM-Powered Social Engineering of Anchors | H | [13 empty] | ● | [37 empty] | ● | ●
RK-CR01 | Credential Revocation Without Due Process | H | [7 empty] | ● | ● | [30 empty] | ● | ●
RK-CY01 | ZKP Implementation Failure | H | [5 empty] | ● | ● | [36 empty] | ● | ●
RK-EX01 | State-Level Coercion of Anchors / IDVPs | H | [9 empty] | ● | ● | [42 empty] | ● | ●
RK-G01 | Genesis Policy Capture | H | ● | ● | [15 empty] | ● | ●
RK-G02 | Governance Transition Failure | H |  | ● | [17 empty] | ●
RK-G03 | Anchor Homogeneity / Collusion Cluster | H |  |  | ● | [7 empty] | ● | [9 empty] | ● | ●
RK-HX02 | Discriminatory Vouching Practices | H |  |  | ● |  |  | ● | [20 empty] | ● | [32 empty] | ●
RK-HX03 | Reputational Harm from Public Revocation | H | [7 empty] | ● | ● | [31 empty] | ● | [19 empty] | ●
RK-ID01 | Sybil Identity Proliferation | H |  |  |  | ● |  |  | ● | [17 empty] | ● | ●
RK-ID02 | Social Graph Privilege Exclusion | H | [5 empty] | ● | [20 empty] | ● | ●
RK-ID03 | IDVP Breach / Cascading Invalidation | H |  |  |  |  | ● |  |  |  | ● | [19 empty] | ● | ●
RK-ID04 | DID Document Manipulation | H | [9 empty] | ● | [20 empty] | ●
RK-NM01 | Personal Network Manager UX Failure | H | [5 empty] | ● | [30 empty] | ● | ●
RK-SY01 | Trust Graph Capture by Coordinated Actor | H |  |  | ● |  |  |  | ● |  |  | ● |  |  |  | ● | [6 empty] | ● |  |  |  |  | ● | [24 empty] | ● | [10 empty] | ●
RK-SY02 | Coordinated Inauthentic Behaviour (CIB) in Governance | H | [14 empty] | ● | ● | [7 empty] | ● | [38 empty] | ●
RK-SY03 | Open Issues Left Unresolved at Scale | H | [6 empty] | ● | [9 empty] | ● | [46 empty] | ● | ●
RK-CR02 | Stale Credential / Expiry Without Renewal Path | M | [7 empty] | ● | [33 empty] | ●
RK-CR03 | Revocation Cascade / Cross-VTC Contamination | M | [8 empty] | ● | [33 empty] | ●
RK-CY02 | Quantum / Algorithm Obsolescence | M | [15 empty] | ● | ● | [28 empty] | ●
RK-EX02 | Registry Censorship / Denial of Service | M | [9 empty] | ● | [5 empty] | ● | [39 empty] | ●
RK-EX03 | Legal / Regulatory Framework Conflict | M | [5 empty] | ● |  |  | ● | [7 empty] | ● | [39 empty] | ● | ●
RK-G04 | Governance Bandwidth Exhaustion | M | [7 empty] | ● | [6 empty] | ● | [7 empty] | ● | ●
RK-HX01 | Chilling Effect on Community Participation | M | [5 empty] | ● |  |  | ● | [22 empty] | ● | [26 empty] | ●
RK-ID05 | M-DID Linkability Across VTCs | M | [5 empty] | ● |  |  | ● | [22 empty] | ●
RK-NM02 | Key Loss / Recovery Failure | M | ● | [37 empty] | ●
RK-SC01 | Over-Disclosure in IDVC Schema | M | [5 empty] | ● |  |  | ● | [23 empty] | ● | ●
RK-SC02 | Credential Schema Ambiguity | M | ● | [33 empty] | ● | ●

## Control Coverage
DTG RAHP – Control Coverage Ranking ¦ Controls and Guardrails ranked by number of High-severity risks addressed ¦ Use this to prioritise what goes into the standard
Interpretation: Controls / Guardrails with the highest High-risk coverage give the greatest harms-prevention return per standards requirement. These are the priority candidates for normative MUST/SHOULD clauses.
Rank | ID | Name | Type | Category | High Risks Addressed | Total Risks Addressed | Risks Addressed (IDs)
1 | GR-07 | Uniqueness Enforcement Mechanism | Guardrail | Technology / Governance | 5 | 5 | RK-ID01, RK-CY01, RK-AI03, RK-SY01, RK-SY03
2 | GR-06 | Privacy-Preserving Proofing Option | Guardrail | Human Experience / Technology | 4 | 8 | RK-ID02, RK-ID05, RK-SC01, RK-NM01, RK-CY01, RK-EX03, RK-HX01, RK-HX02
3 | GR-09 | Privacy-Preserving Revocation Disclosure | Guardrail | Technology / Governance | 3 | 8 | RK-ID03, RK-ID05, RK-SC01, RK-CR01, RK-CR03, RK-EX03, RK-HX01, RK-HX03
4 | GR-10 | Multi-Party Registry Write Authorisation | Guardrail | Technology / Governance | 3 | 4 | RK-ID04, RK-EX01, RK-EX02, RK-SY01
5 | GR-03 | Trust Anchor Diversity Policy | Guardrail | Governance / Human Experience | 3 | 3 | RK-G03, RK-HX02, RK-SY01
6 | GR-14 | Non-Human Actor Detection | Guardrail | Technology / Governance | 3 | 3 | RK-AI03, RK-AI04, RK-SY01
7 | CT-08 | Uniqueness Enforcement Mechanism | Control | Technical | 3 | 3 | RK-ID01, RK-AI03, RK-SY03
8 | GR-08 | Revocation Due Process | Guardrail | Governance / Human Experience | 2 | 4 | RK-G04, RK-CR01, RK-CR02, RK-HX03
9 | GR-02 | Time-Bounded Initiator Authority | Guardrail | Governance | 2 | 2 | RK-G01, RK-G02
10 | GR-11 | Jurisdictional Diversity for Key Parties | Guardrail | Governance | 2 | 2 | RK-G03, RK-EX01
11 | GR-12 | Agent Delegation Scope Constraint | Guardrail | Technology / Governance | 2 | 2 | RK-AI01, RK-AI02
12 | CT-04 | Trust Anchor Diversity Policy | Control | Governance | 2 | 2 | RK-G03, RK-SY01
13 | CT-09 | Vouching Pattern Anomaly Detection | Control | Technical | 2 | 2 | RK-ID01, RK-SY01
14 | CT-10 | Non-Discriminatory Admission Criteria | Control | Governance | 2 | 2 | RK-ID02, RK-HX02
15 | CT-24 | Privacy-Preserving Revocation Disclosure | Control | Technical | 2 | 2 | RK-CR01, RK-HX03
16 | CT-33 | Non-Human Activity Rate-Limiting | Control | Technical | 2 | 2 | RK-AI03, RK-AI04
17 | CT-34 | Behavioural Anomaly Detection for Non-Human Actors | Control | Technical | 2 | 2 | RK-AI03, RK-SY01
18 | CT-45 | Multi-Party Registry Write Authorisation | Control | Technical | 2 | 2 | RK-SY01, RK-EX01
19 | GR-01 | Genesis Policy Documentation | Guardrail | Governance | 1 | 3 | RK-G01, RK-SC02, RK-NM02
20 | GR-16 | Formal Threat Model Publication | Guardrail | Governance | 1 | 3 | RK-CY02, RK-EX02, RK-SY02
21 | GR-17 | Open Issues Risk Acceptance | Guardrail | Governance | 1 | 3 | RK-CY02, RK-EX03, RK-SY03
22 | GR-15 | Complaint and Appeals Rate-Limiting | Guardrail | Governance / Human Experience | 1 | 2 | RK-G04, RK-SY02
23 | CT-07 | Complaint / Appeals Rate-Limiting | Control | Technical | 1 | 2 | RK-G04, RK-SY02
24 | CT-48 | Threat Model Maintenance | Control | Governance | 1 | 2 | RK-SY03, RK-CY02
25 | GR-04 | Reciprocal VRC Requirement | Guardrail | Technology / Governance | 1 | 1 | RK-ID01
26 | GR-05 | IDVP Registry Standing | Guardrail | Technology / Governance | 1 | 1 | RK-ID03
27 | GR-13 | Agent Audit Logging | Guardrail | Technology / Governance | 1 | 1 | RK-AI01
28 | CT-01 | Version-Controlled Public Genesis Policy | Control | Procedural | 1 | 1 | RK-G01
29 | CT-02 | Independent Governance Review at Genesis | Control | Governance | 1 | 1 | RK-G01
30 | CT-03 | Governance Transition Milestones | Control | Governance | 1 | 1 | RK-G02
31 | CT-05 | Anchor Clustering Metric Monitoring | Control | Technical | 1 | 1 | RK-G03
32 | CT-11 | Alternative Identity Proofing Paths | Control | Procedural | 1 | 1 | RK-ID02
33 | CT-12 | IDVP Security Approval Criteria | Control | Governance | 1 | 1 | RK-ID03
34 | CT-13 | IDVP Deregistration Handling Protocol | Control | Procedural | 1 | 1 | RK-ID03
35 | CT-14 | DID Document Integrity Verification | Control | Technical | 1 | 1 | RK-ID04
36 | CT-20 | Sovereign Wallet UX Design Principles | Control | UX | 1 | 1 | RK-NM01
37 | CT-21 | Non-Technical User Onboarding Testing | Control | UX | 1 | 1 | RK-NM01
38 | CT-23 | Mandatory Pre-Revocation Notice | Control | Governance | 1 | 1 | RK-CR01
39 | CT-27 | Audited ZKP Library Requirement | Control | Technical | 1 | 1 | RK-CY01
40 | CT-28 | ZKP Conformance Testing | Control | Technical | 1 | 1 | RK-CY01
41 | CT-30 | Cryptographic Delegation Scope Constraints | Control | Technical | 1 | 1 | RK-AI01
42 | CT-31 | Short-Lived Agent Credentials | Control | Technical | 1 | 1 | RK-AI01
43 | CT-32 | Agent Liveness Check on Operator VMC | Control | Technical | 1 | 1 | RK-AI02
44 | CT-35 | Anchor Awareness of AI Social Engineering | Control | Procedural | 1 | 1 | RK-AI04
45 | CT-36 | Out-of-Band Verification for High-Stakes Vouching | Control | Procedural | 1 | 1 | RK-AI04
46 | CT-37 | Jurisdictional Diversity of Key Parties | Control | Governance | 1 | 1 | RK-EX01
47 | CT-38 | Legal Coercion Response Protocol | Control | Procedural | 1 | 1 | RK-EX01
48 | CT-43 | Governing Body Accountability for Systematic Exclusion | Control | Governance | 1 | 1 | RK-HX02
49 | CT-44 | Remediation Pathway After Overturned Revocation | Control | Governance | 1 | 1 | RK-HX03
50 | CT-46 | Coordinated Behaviour Detection in Governance | Control | Technical | 1 | 1 | RK-SY02
51 | CT-47 | Formal Open Issues Mitigation Plan | Control | Governance | 1 | 1 | RK-SY03
52 | CT-15 | Pseudonymous Per-VTC M-DID Design | Control | Technical | 0 | 2 | RK-ID05, RK-HX01
53 | CT-06 | Governance Capacity Planning | Control | Procedural | 0 | 1 | RK-G04
54 | CT-16 | Minimum-Necessary IDVC Attribute Set | Control | Governance | 0 | 1 | RK-SC01
55 | CT-17 | Data Minimisation Audit | Control | Procedural | 0 | 1 | RK-SC01
56 | CT-18 | Normative Credential Schema Publication | Control | Technical | 0 | 1 | RK-SC02
57 | CT-19 | Conformance Test Suite | Control | Technical | 0 | 1 | RK-SC02
58 | CT-22 | Key Recovery Mechanism | Control | Technical | 0 | 1 | RK-NM02
59 | CT-25 | Credential Renewal Workflow | Control | Technical | 0 | 1 | RK-CR02
60 | CT-26 | VTC-Scoped Revocation | Control | Technical | 0 | 1 | RK-CR03
61 | CT-29 | Algorithm Agility and Migration Pathway | Control | Technical | 0 | 1 | RK-CY02
62 | CT-39 | Distributed Registry Architecture | Control | Technical | 0 | 1 | RK-EX02
63 | CT-40 | Legal Review of Credential Schemas | Control | Legal | 0 | 1 | RK-EX03
64 | CT-41 | Open Issues Regulatory Risk Acceptance | Control | Governance | 0 | 1 | RK-EX03
65 | CT-42 | Anonymous Membership Option | Control | Technical | 0 | 1 | RK-HX01

## Risk x Use Case
DTG RAHP – Risk × Use Case ¦ Which risks arise in which User Stories and Scenarios
Risk ID | Risk Name | Cat | Sev | US-01 | US-02 | US-03 | US-04 | US-05 | US-06 | US-07 | US-08 | US-09 | US-10 | US-11 | US-12 | SC-01 | SC-02 | SC-03 | SC-04 | SC-05 | SC-06 | SC-07 | SC-08 | SC-09 | SC-10 | SC-11 | SC-12
RK-AI01 | Agent Credential Scope Creep | AI Agents | High | [7 empty] | ● | ● | [12 empty] | ● | ●
RK-AI02 | Stale Agent After Operator Revocation | AI Agents | High | [7 empty] | ● | [13 empty] | ●
RK-AI03 | AI-Mediated Sybil Generation at Scale | AI Agents | High | [8 empty] | ● | ● | [8 empty] | ● |  |  |  | ●
RK-AI04 | LLM-Powered Social Engineering of Anchors | AI Agents | High |  |  | ● | [5 empty] | ● | [13 empty] | ●
RK-CR01 | Credential Revocation Without Due Process | Credentials | High | [5 empty] | ● | [11 empty] | ●
RK-CY01 | ZKP Implementation Failure | Cryptography | High |  |  |  | ● | ● | [10 empty] | ●
RK-EX01 | State-Level Coercion of Anchors / IDVPs | External | High | [10 empty] | ● | [9 empty] | ●
RK-G01 | Genesis Policy Capture | Governance | High | ● | [11 empty] | ●
RK-G02 | Governance Transition Failure | Governance | High | ● | ● | [10 empty] | ● | ●
RK-G03 | Anchor Homogeneity / Collusion Cluster | Governance | High |  | ● | ● | [10 empty] | ● | [6 empty] | ●
RK-HX02 | Discriminatory Vouching Practices | Human Experience | High |  |  | ● | ● | [10 empty] | ●
RK-HX03 | Reputational Harm from Public Revocation | Human Experience | High | [5 empty] | ● | [11 empty] | ●
RK-ID01 | Sybil Identity Proliferation | Identity | High | [6 empty] | ● |  |  | ● | [8 empty] | ●
RK-ID02 | Social Graph Privilege Exclusion | Identity | High |  |  |  | ● | [10 empty] | ● | ●
RK-ID03 | IDVP Breach / Cascading Invalidation | Identity | High |  |  |  |  | ● | [11 empty] | ●
RK-ID04 | DID Document Manipulation | Identity | High | [6 empty] | ● | [12 empty] | ●
RK-NM01 | Personal Network Manager UX Failure | Network Managers | High | ● | ● | ● | ● | [8 empty] | ● | ● | ● | ●
RK-SY01 | Trust Graph Capture by Coordinated Actor | Systemic | High | [8 empty] | ● | ● | [8 empty] | ● |  |  |  | ●
RK-SY02 | Coordinated Inauthentic Behaviour (CIB) in Governance | Systemic | High | [11 empty] | ● | [11 empty] | ●
RK-SY03 | Open Issues Left Unresolved at Scale | Systemic | High | [6 empty] | ● | [11 empty] | ● | ●
RK-CR02 | Stale Credential / Expiry Without Renewal Path | Credentials | Medium |  |  |  |  | ● | ● | [10 empty] | ●
RK-CR03 | Revocation Cascade / Cross-VTC Contamination | Credentials | Medium | [5 empty] | ● | [11 empty] | ●
RK-CY02 | Quantum / Algorithm Obsolescence | Cryptography | Medium | [6 empty] | ● | [12 empty] | ●
RK-EX02 | Registry Censorship / Denial of Service | External | Medium | [6 empty] | ● |  |  |  | ● | [8 empty] | ● | ●
RK-EX03 | Legal / Regulatory Framework Conflict | External | Medium | ● |  |  |  | ● | [7 empty] | ● |  |  | ●
RK-G04 | Governance Bandwidth Exhaustion | Governance | Medium | [5 empty] | ● | [5 empty] | ● | [5 empty] | ● | [5 empty] | ●
RK-HX01 | Chilling Effect on Community Participation | Human Experience | Medium |  |  |  | ● |  | ● | [14 empty] | ●
RK-ID05 | M-DID Linkability Across VTCs | Identity | Medium |  |  |  | ● |  | ● | [14 empty] | ●
RK-NM02 | Key Loss / Recovery Failure | Network Managers | Medium |  |  | ● | ● | [10 empty] | ● | ●
RK-SC01 | Over-Disclosure in IDVC Schema | Schemas | Medium |  |  |  |  | ● | [10 empty] | ●
RK-SC02 | Credential Schema Ambiguity | Schemas | Medium | ● |  |  |  | ● |  | ● | [5 empty] | ● |  |  | ●
RK-SC03 | VRC Over-Disclosure — Rich Data in Core Edge | Schemas | Medium |  |  |  | ● |  | ● | [8 empty] | ● | ●
RK-SC04 | M-DID Bootstrapping Exception Undermines R-DID Privacy | Schemas | Medium |  |  |  | ● |  | ● |  |  |  |  | ● |  | ● | ● | [6 empty] | ●
RK-CR04 | Endorsement Credential (VEC) Manipulation | Credentials | Medium |  |  | ● | [6 empty] | ● |  | ● | [6 empty] | ● |  |  |  |  | ●
RK-G05 | Governanceless VTC Claiming Credential Compliance | Governance | Medium | ● |  |  | ● | [8 empty] | ●

## Trust Metrics
DTG RAHP – Trust & Confidence Metrics ¦ Metrics personas want to increase (or bad actors want to suppress)
Metric ID | Metric Name | Category | Description | Personas Who WANT This Metric | Personas Who DISLIKE This Metric
M-01 | Anchor Diversity Index | Governance | Measures the geographic, organisational, and cultural spread of trust anchors across the trust graph. A higher score indicates greater decentralisation and resilience to collusion. | D1, D2, D3, D5, D6 | B1, B2
M-02 | Time to Revocation Notice (SLA) | Governance | The elapsed time between a revocation decision and formal notification to the affected member. Lower is better for due process compliance. | D5, D6 | B2, B3
M-03 | VRC Reciprocity Rate | Identity | Proportion of VMC issuances where a valid reciprocal VRC exchange was confirmed. A low rate indicates PEP enforcement failures. | D1, D2, D4, D6 | B1
M-04 | IDVC Issuer Verification Rate | Identity | Proportion of Phase 4 admissions where the IDVP DID was verified against the trust registry before VMC issuance. Should be 100%. | D4, D6 | B1
M-05 | Anomaly Detection Hit Rate (Vouching Patterns) | Security | Rate at which coordinated or anomalous vouching patterns are flagged by the VTA analytics engine. Higher is better for Sybil resistance. | D6, D2 | B1, B3
M-06 | Registry Write Authorisation Failure Rate | Security | Rate at which single-party registry write attempts are rejected. Should be 100% — any successful single-party write is a governance failure. | D6, D1 | B1, B2
M-07 | Appeals Process Response Time | Human Experience | Median time from appeal submission to formal response from the governing body. Lower indicates a more effective due process mechanism. | D3, D5 | B2, B3
M-08 | Agent Credential Scope Violation Rate | AI Agents | Rate at which AI agents attempt operations outside their delegated credential scope. Any non-zero rate indicates a governance or enforcement failure. | M1, D6 | M2, B1
M-09 | ZKP / Selective Disclosure Uptake Rate | Privacy | Proportion of Phase 4 applicants using privacy-preserving proofing options rather than raw IDVC disclosure. Higher indicates better privacy protection. | D3, D4, D5 | B2
M-10 | Jurisdictional Concentration of Key Parties | Governance | Proportion of trust anchors and IDVPs located within a single legal jurisdiction. Lower is better — high concentration indicates coercion risk. | D1, D6 | B2
M-11 | Bad-Faith Appeals Rate | Governance | Proportion of appeal submissions subsequently determined to be coordinated or bad-faith. Rate-limiting and CIB detection should suppress this. | D5, D6 | B3
M-12 | Member Admission Denial Rate | Human Experience | Proportion of well-formed membership applications that are denied. A high rate may indicate discriminatory gatekeeping; a very low rate may indicate weak admission enforcement. | D3 | B1
M-13 | Credential Expiry-to-Renewal Latency | Lifecycle | Time between credential expiry notification and successful renewal. Relevant for both human members and AI agents. Longer latency increases operational disruption. | D5, M1 | M2
M-14 | Sybil Cluster Detection Rate | Security | Rate at which coordinated multi-M-DID registration attempts are identified and blocked. A primary uniqueness enforcement metric. | D6, D1, D2 | B1
M-15 | DID Document Integrity Verification Rate | Cryptography | Proportion of DID document resolutions where the VTA confirms document integrity before relying on the resolved content. Should be 100%. | D6, D4 | B1, B2
M-16 | Governance Body Response Time to Security Findings | Governance | Elapsed time from submission of a security researcher's findings to formal governance acknowledgement and response. Lower supports responsible disclosure and trust. | D6 | B1, B2
M-17 | Cross-VTC Revocation Contamination Rate | Lifecycle | Rate at which a revocation in one VTC propagates (intentionally or accidentally) to unrelated VTCs where the member holds credentials. Should be governed and scoped. | D5, D3 | B2
M-18 | Rate-Limiting Trigger Accuracy (AI / Non-Human) | AI Agents | Proportion of rate-limiting events that correctly target non-human or adversarial activity, avoiding false positives on legitimate benign agents. | M1, D6 | M2, B1
LEGEND
Green = Personas who want this metric to be high / visible
Red = Personas (typically bad actors) who dislike this metric or want it suppressed

## Metrics x Personas
DTG RAHP – Metrics × Personas Pivot ¦ ✓ = Wants metric ¦ ✗ = Dislikes / wants suppressed ¦ (blank) = Not directly applicable
Metric ID | Metric Name | D1 | D2 | D3 | D4 | D5 | D6 | M1 | M2 | B1 | B2 | B3
M-01 | Anchor Diversity Index [Governance] | bar: D1 to D6; B1 to B2
M-02 | Time to Revocation Notice (SLA) [Governance] | bar: D1 to B3
M-03 | VRC Reciprocity Rate [Identity] | bar: D1 to D6; B1 to B3
M-04 | IDVC Issuer Verification Rate [Identity] | bar: D1 to D6; B1 to B3
M-05 | Anomaly Detection Hit Rate (Vouching Patterns) [Security] | bar: D1 to D6; B1 to B3
M-06 | Registry Write Authorisation Failure Rate [Security] | bar: D1 to D6; B1 to B2
M-07 | Appeals Process Response Time [Human Experience] | bar: D1 to B3
M-08 | Agent Credential Scope Violation Rate [AI Agents] | bar: D1 to B3
M-09 | ZKP / Selective Disclosure Uptake Rate [Privacy] | bar: D1 to B2
M-10 | Jurisdictional Concentration of Key Parties [Governance] | bar: D1 to B2
M-11 | Bad-Faith Appeals Rate [Governance] | bar: D1 to B3
M-12 | Member Admission Denial Rate [Human Experience] | bar: D1 to B3
M-13 | Credential Expiry-to-Renewal Latency [Lifecycle] | bar: D1 to B3
M-14 | Sybil Cluster Detection Rate [Security] | bar: D1 to D6; B1 to B3
M-15 | DID Document Integrity Verification Rate [Cryptography] | bar: D1 to D6; B1 to B2
M-16 | Governance Body Response Time to Security Findings [Governance] | bar: D1 to D6; B1 to B2
M-17 | Cross-VTC Revocation Contamination Rate [Lifecycle] | bar: D1 to B2
M-18 | Rate-Limiting Trigger Accuracy (AI / Non-Human) [AI Agents] | bar: D1 to B3
Persona → | Full Name | Daniel Wright – Initiator | Laila Hassan – Trust Anchor | Ahmed Khan – New Member | Elena Rossi – IDVP | Sophie Dubois – Revocation Subject | Tomasz Kowalski – Security Researcher | Aether – Benign AI Agent | Phantom – Malign AI Agent | Viktor – Sybil Operator | State Security Directorate | The Collective – Disruptor

## Risk x Metrics (Pivot)
DTG RAHP – Risk × Metrics Pivot ¦ Read across to see metrics triggered by a risk ¦ Read down to see all risks a metric helps measure
Risk ID | Risk Name | Sev | M-01 | M-02 | M-03 | M-04 | M-05 | M-06 | M-07 | M-08 | M-09 | M-10 | M-11 | M-12 | M-13 | M-14 | M-15 | M-16 | M-17 | M-18
→ Metric | Short Name |  | Anchor Diversity Index | Time to Revocation Notice (SLA) | VRC Reciprocity Rate | IDVC Issuer Verification Rate | Anomaly Detection Hit Rate (Vouching) | Registry Write Auth Failure Rate | Appeals Process Response Time | Agent Credential Scope Violation Rate | ZKP / Selective Disclosure Uptake | Jurisdictional Concentration | Bad-Faith Appeals Rate | Member Admission Denial Rate | Credential Expiry-to-Renewal Latency | Sybil Cluster Detection Rate | DID Document Integrity Verification Rate | Governance Response Time to Security Findings | Cross-VTC Revocation Contamination Rate | Rate-Limiting Trigger Accuracy (AI/NHI)
RK-G01 | Genesis Policy Capture | H | ● | [14 empty] | ●
RK-G02 | Governance Transition Failure | H | ● | [14 empty] | ●
RK-G03 | Anchor Homogeneity / Collusion Cluster | H | ● |  |  |  | ● |  |  |  |  | ●
RK-G04 | Governance Bandwidth Exhaustion | M | [6 empty] | ● |  |  |  | ●
RK-ID01 | Sybil Identity Proliferation | H |  |  | ● |  | ● | [8 empty] | ●
RK-ID02 | Social Graph Privilege Exclusion | H | [8 empty] | ● |  |  | ●
RK-ID03 | IDVP Breach / Cascading Invalidation | H |  |  |  | ● | [8 empty] | ●
RK-ID04 | DID Document Manipulation | H | [5 empty] | ● | [8 empty] | ●
RK-ID05 | M-DID Linkability Across VTCs | M | [8 empty] | ● | [7 empty] | ●
RK-SC01 | Over-Disclosure in IDVC Schema | M |  |  |  | ● |  |  |  |  | ●
RK-SC02 | Credential Schema Ambiguity | M |  |  |  | ● | [10 empty] | ●
RK-NM01 | Personal Network Manager UX Failure | H |  |  | ● | [8 empty] | ●
RK-NM02 | Key Loss / Recovery Failure | M | [12 empty] | ●
RK-CR01 | Credential Revocation Without Due Process | H |  | ● |  |  |  |  | ● |  | ●
RK-CR02 | Stale Credential / Expiry Without Renewal Path | M |  | ● | [10 empty] | ●
RK-CR03 | Revocation Cascade / Cross-VTC Contamination | M | [8 empty] | ● | [7 empty] | ●
RK-CY01 | ZKP Implementation Failure | H | [8 empty] | ● | [5 empty] | ●
RK-CY02 | Quantum / Algorithm Obsolescence | M | [14 empty] | ● | ●
RK-AI01 | Agent Credential Scope Creep | H | [7 empty] | ● | [9 empty] | ●
RK-AI02 | Stale Agent After Operator Revocation | H | [7 empty] | ● |  |  |  |  | ●
RK-AI03 | AI-Mediated Sybil Generation at Scale | H | [13 empty] | ● |  |  |  | ●
RK-AI04 | LLM-Powered Social Engineering of Anchors | H |  |  |  |  | ● | [12 empty] | ●
RK-EX01 | State-Level Coercion of Anchors / IDVPs | H | [5 empty] | ● |  |  |  | ●
RK-EX02 | Registry Censorship / Denial of Service | M | [5 empty] | ● | [8 empty] | ●
RK-EX03 | Legal / Regulatory Framework Conflict | M |  |  |  | ● |  |  |  |  | ●
RK-HX01 | Chilling Effect on Community Participation | M | [8 empty] | ● |  |  | ●
RK-HX02 | Discriminatory Vouching Practices | H |  |  |  |  | ● | [6 empty] | ●
RK-HX03 | Reputational Harm from Public Revocation | H |  | ● | [14 empty] | ●
RK-SY01 | Trust Graph Capture by Coordinated Actor | H | ● |  |  |  | ● | [8 empty] | ●
RK-SY02 | Coordinated Inauthentic Behaviour (CIB) in Governance | H |  |  |  |  | ● | [5 empty] | ●
RK-SY03 | Open Issues Left Unresolved at Scale | H | [13 empty] | ● |  | ●
RK-SC03 | VRC Over-Disclosure — Rich Data in Core Edge | M | [8 empty] | ●
RK-SC04 | M-DID Bootstrapping Exception Undermines R-DID Privacy | M | [8 empty] | ● | [7 empty] | ●
RK-CR04 | Endorsement Credential (VEC) Manipulation | M |  |  |  |  | ● | [8 empty] | ●
RK-G05 | Governanceless VTC Claiming Credential Compliance | M | ● | [14 empty] | ●

## Metric Detail
DTG RAHP – Metric Detail ¦ For each metric: risks it measures, personas who want it, personas who dislike it
Metric ID | Metric Name | Category | Risks Measured | Personas Who WANT This High | Personas Who DISLIKE This
M-01 | Anchor Diversity Index | Governance | RK-G01, RK-G02, RK-G03, RK-G05, RK-SY01 | D1: Daniel Wright – Initiator D2: Laila Hassan – Trust Anchor D3: Ahmed Khan – New Member D5: Sophie Dubois – Revocation Subject D6: Tomasz Kowalski – Researcher | B1: Viktor – Sybil Operator B2: State Security Directorate
M-02 | Time to Revocation Notice (SLA) | Governance | RK-CR01, RK-CR02, RK-HX03 | D5: Sophie Dubois – Revocation Subject D6: Tomasz Kowalski – Researcher | B2: State Security Directorate B3: The Collective – Disruptor
M-03 | VRC Reciprocity Rate | Identity | RK-ID01, RK-NM01 | D1: Daniel Wright – Initiator D2: Laila Hassan – Trust Anchor D4: Elena Rossi – IDVP D6: Tomasz Kowalski – Researcher | B1: Viktor – Sybil Operator
M-04 | IDVC Issuer Verification Rate | Identity | RK-ID03, RK-SC01, RK-SC02, RK-EX03 | D4: Elena Rossi – IDVP D6: Tomasz Kowalski – Researcher | B1: Viktor – Sybil Operator
M-05 | Anomaly Detection Hit Rate (Vouching) | Security | RK-G03, RK-ID01, RK-CR04, RK-AI04, RK-HX02, RK-SY01, RK-SY02 | D6: Tomasz Kowalski – Researcher D2: Laila Hassan – Trust Anchor | B1: Viktor – Sybil Operator B3: The Collective – Disruptor
M-06 | Registry Write Auth Failure Rate | Security | RK-ID04, RK-EX01, RK-EX02 | D6: Tomasz Kowalski – Researcher D1: Daniel Wright – Initiator | B1: Viktor – Sybil Operator B2: State Security Directorate
M-07 | Appeals Process Response Time | Human Experience | RK-G04, RK-CR01 | D3: Ahmed Khan – New Member D5: Sophie Dubois – Revocation Subject | B2: State Security Directorate B3: The Collective – Disruptor
M-08 | Agent Credential Scope Violation Rate | AI Agents | RK-AI01, RK-AI02 | M1: Aether – Benign AI Agent D6: Tomasz Kowalski – Researcher | M2: Phantom – Malign AI Agent B1: Viktor – Sybil Operator
M-09 | ZKP / Selective Disclosure Uptake | Privacy | RK-ID02, RK-ID05, RK-SC01, RK-SC03, RK-SC04, RK-CR01, RK-CR03, RK-CY01, RK-EX03, RK-HX01 | D3: Ahmed Khan – New Member D4: Elena Rossi – IDVP D5: Sophie Dubois – Revocation Subject | B2: State Security Directorate
M-10 | Jurisdictional Concentration | Governance | RK-G03, RK-EX01 | D1: Daniel Wright – Initiator D6: Tomasz Kowalski – Researcher | B2: State Security Directorate
M-11 | Bad-Faith Appeals Rate | Governance | RK-G04, RK-SY02 | D5: Sophie Dubois – Revocation Subject D6: Tomasz Kowalski – Researcher | B3: The Collective – Disruptor
M-12 | Member Admission Denial Rate | Human Experience | RK-ID02, RK-NM01, RK-HX01, RK-HX02 | D3: Ahmed Khan – New Member | B1: Viktor – Sybil Operator
M-13 | Credential Expiry-to-Renewal Latency | Lifecycle | RK-ID03, RK-NM02, RK-CR02, RK-AI02 | D5: Sophie Dubois – Revocation Subject M1: Aether – Benign AI Agent | M2: Phantom – Malign AI Agent
M-14 | Sybil Cluster Detection Rate | Security | RK-ID01, RK-CR04, RK-AI03, RK-SY01, RK-SY03 | D6: Tomasz Kowalski – Researcher D1: Daniel Wright – Initiator D2: Laila Hassan – Trust Anchor | B1: Viktor – Sybil Operator
M-15 | DID Document Integrity Verification Rate | Cryptography | RK-ID04, RK-SC02, RK-CY01, RK-CY02, RK-EX02 | D6: Tomasz Kowalski – Researcher D4: Elena Rossi – IDVP | B1: Viktor – Sybil Operator B2: State Security Directorate
M-16 | Governance Response Time to Security Findings | Governance | RK-G01, RK-G02, RK-G05, RK-CY02, RK-SY03 | D6: Tomasz Kowalski – Researcher | B1: Viktor – Sybil Operator B2: State Security Directorate
M-17 | Cross-VTC Revocation Contamination Rate | Lifecycle | RK-ID05, RK-SC04, RK-CR03, RK-HX03 | D5: Sophie Dubois – Revocation Subject D3: Ahmed Khan – New Member | B2: State Security Directorate
M-18 | Rate-Limiting Trigger Accuracy (AI/NHI) | AI Agents | RK-AI01, RK-AI03, RK-AI04 | M1: Aether – Benign AI Agent D6: Tomasz Kowalski – Researcher | M2: Phantom – Malign AI Agent B1: Viktor – Sybil Operator